## Performance Proj
Housing | Quarterly Projection of Housing Units | Total Projection of Housing Units | Quarterly Actual Number of Housing Units | Total Housing Units
2016-10-01 | 0 | 0 | 0 | 0
2017-01-01 | 1 | 1 | 0 | 0
2017-04-01 | 6 | 7 | 0 | 0
2017-07-01 | 20 | 27 | 0 | 0
2017-10-01 | 25 | 52 | 5 | 5
2018-01-01 | 15 | 67 | 10 | 15
2018-04-01 | 10 | 77 | 19 | 34
2018-07-01 | 20 | 97 | 9 | 43
2018-10-01 | 25 | 122 | 11 | 54
2019-01-01 | 15 | 137 | 6 | 60
2019-04-01 | 10 | 147 | 8 | 68
2019-07-01 | 14 | 161 | 51 | 119
2019-10-01 | 20 | 181 | 78 | 197
2020-01-01 | 20 | 201 | 2 | 199
2020-04-01 | 20 | 221 | 16 | 215
2020-07-01 | 20 | 241 | 10 | 225
2020-10-01 | 25 | 266 | 11 | 236
2021-01-01 | 23 | 289 | 8 | 244
2021-04-01 | 31 | 320 | 6 | 250
2021-07-01 | 0 | 320 | 14 | 264
2021-10-01 | 0 | 320 | 8 | 272
2022-01-01 | 0 | 320 | 3 | 275
2022-04-01 | 0 | 320 | 36 | 311
Public Facilities | Quarterly Projection of Watershed Practices & Public Facilities | Total Projection of Watershed Practices & Public Facilities | Quarterly Actual Number of Watershed Practices & Public Facilities | Total Watersheds Practices & Public Facilities | PROJECTED Watershed Practices | ACTUAL Watershed Practices | PROJECTED Construction/ Reconstruction of water/sewer lines or systems | ACTUAL Construction/ Reconstruction of water/sewer lines or systems | PROJECTED Linear Feet | ACTUAL Linear Feet
2016-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-07-01 | 33.4496 | 33.4496 | 0 | 0 | 33.4496 | 0 | 0 | 0 | 0 | 0
2017-10-01 | 33.4496 | 66.8991 | 0 | 0 | 33.4496 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 33.4496 | 100.3487 | 0 | 0 | 33.4496 | 0 | 0 | 0 | 0 | 0
2018-04-01 | 33.4496 | 133.7983 | 2 | 2 | 33.4496 | 0 | 0 | 2 | 0 | 0
2018-07-01 | 33.4496 | 167.2478 | 0 | 2 | 33.4496 | 0 | 0 | 0 | 0 | 0
2018-10-01 | 33.4496 | 200.6974 | 0 | 2 | 33.4496 | 0 | 0 | 0 | 0 | 0
2019-01-01 | 33.4496 | 234.147 | 0 | 2 | 33.4496 | 0 | 0 | 0 | 0 | 0
2019-04-01 | 33.4496 | 267.5965 | 0 | 2 | 33.4496 | 0 | 0 | 0 | 0 | 0
2019-07-01 | 33.4496 | 301.0461 | 0 | 2 | 33.4496 | 0 | 0 | 0 | 0 | 0
2019-10-01 | 33.4496 | 334.4957 | 50 | 52 | 33.4496 | 50 | 0 | 0 | 0 | 0
2020-01-01 | 33.4496 | 367.9452 | 0 | 52 | 33.4496 | 0 | 0 | 0 | 0 | 0
2020-04-01 | 33.4496 | 401.3948 | 75 | 127 | 33.4496 | 75 | 0 | 0 | 0 | 0
2020-07-01 | 33.4496 | 434.8444 | 75 | 202 | 33.4496 | 75 | 0 | 0 | 0 | 0
2020-10-01 | 33.4496 | 468.2939 | 12 | 214 | 33.4496 | 12 | 0 | 0 | 0 | 0
2021-01-01 | 33.4496 | 501.7435 | 8 | 222 | 33.4496 | 8 | 0 | 0 | 0 | 0
2021-04-01 | 33.4496 | 535.1931 | 26 | 248 | 33.4496 | 26 | 0 | 0 | 0 | 0
2021-07-01 | 35.4496 | 570.6426 | 77 | 325 | 33.4496 | 77 | 2 | 0 | 0 | 0
2021-10-01 | 33.4496 | 604.0922 | 81 | 406 | 33.4496 | 81 | 0 | 0 | 0 | 0
2022-01-01 | 33.4496 | 637.5418 | 123 | 529 | 33.4496 | 123 | 0 | 0 | 0 | 0
2022-04-01 | 36.4496 | 673.9913 | 155 | 684 | 33.4496 | 152 | 3 | 3 | 0 | 0
2022-07-01 | 20.0996 | 694.0909 | 3 | 687 | 20.0996 | 3 | 0 | 0 | 0 | 0
2022-10-01 | 13.9091 | 708 | 0 | 687 | 7.9091 | 0 | 6 | 0 | 18200 | 0
2023-01-01 | 0 | 708 | 0 | 687 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 697 | 682 | 11 | 5 | 18200 | 0
Planning | Quarterly Projection Plans or Planning Products | Total Projection of Plans or Planning Products | Quarterly Actual Plans or Planning Products | Total Plans or Planning Products
2016-10-01 | 0 | 0 | 7 | 7
2017-01-01 | 0 | 0 | 9 | 16
2017-04-01 | 1 | 1 | 11 | 27
2017-07-01 | 0 | 1 | 10 | 37
2017-10-01 | 0 | 1 | 6 | 43
2018-01-01 | 0 | 1 | 12 | 55
2018-04-01 | 0 | 1 | 5 | 60
2018-07-01 | 0 | 1 | 22 | 82
2018-10-01 | 0 | 1 | 41 | 123
2019-01-01 | 0 | 1 | 7 | 130
2019-04-01 | 0 | 1 | 15 | 145
2019-07-01 | 0 | 1 | 8 | 153
2019-10-01 | 0 | 1 | 9 | 162
2020-01-01 | 6 | 7 | 7 | 169
2020-04-01 | 2 | 9 | 15 | 184
2020-07-01 | 0 | 9 | 5 | 189
2020-10-01 | 0 | 9 | 16 | 205
2021-01-01 | 200 | 209 | 6 | 211
2021-04-01 | 15 | 224 | 15 | 226
2021-07-01 | 7 | 231 | 54 | 280
2021-10-01 | 8 | 239 | 9 | 289
2022-01-01 | 0 | 239 | 0 | 289
2022-04-01 | 0 | 239 | 0 | 289
2022-07-01 | 0 | 239 | 19 | 308
2022-10-01 | 88 | 327 | 19 | 327

## Financial Proj
Housing | Quarterly Expenditures | Projected Expenditures | Quarterly Actual Expenditures | Actual Expenditures
2016-10-01 | 353216.3043 | 353216.3043 | 0 | 0
2017-01-01 | 353216.3043 | 706432.6087 | 0 | 0
2017-04-01 | 353216.3043 | 1059648.913 | 0 | 0
2017-07-01 | 353216.3043 | 1412865.2174 | 0 | 0
2017-10-01 | 353216.3043 | 1766081.5217 | 0 | 0
2018-01-01 | 353216.3043 | 2119297.8261 | 0 | 0
2018-04-01 | 353216.3043 | 2472514.1304 | 239506 | 239506
2018-07-01 | 353216.3043 | 2825730.4348 | 165144 | 404650
2018-10-01 | 353216.3043 | 3178946.7391 | 621214 | 1025864
2019-01-01 | 353216.3043 | 3532163.0435 | 0 | 1025864
2019-04-01 | 353216.3043 | 3885379.3478 | 707453 | 1733317
2019-07-01 | 353216.3043 | 4238595.6522 | 460333 | 2193650
2019-10-01 | 353216.3043 | 4591811.9565 | 1247602 | 3441252
2020-01-01 | 353216.3043 | 4945028.2609 | 663988 | 4105240
2020-04-01 | 353216.3043 | 5298244.5652 | 507649 | 4612889
2020-07-01 | 353216.3043 | 5651460.8696 | 0 | 4612889
2020-10-01 | 353216.3043 | 6004677.1739 | 550672 | 5163561
2021-01-01 | 353216.3043 | 6357893.4783 | 453037 | 5616598
2021-04-01 | 353216.3043 | 6711109.7826 | 226769 | 5843367
2021-07-01 | 353216.3043 | 7064326.087 | 899588 | 6742955
2021-10-01 | 353216.3043 | 7417542.3913 | 0 | 6742955
2022-01-01 | 353216.3043 | 7770758.6957 | 585843 | 7328798
2022-04-01 | 353216.3043 | 8123975 | 157932 | 7486730
2022-07-01 | 0 | 8123975 | 637245 | 8123975
2022-10-01 | 0 | 8123975 | 0 | 8123975 | BALANCE
2023-01-01 | 0 | 8123975 | 0 | 8123975 | 0
Non-Housing | Quarterly Expenditures | Projected Expenditures | Quarterly Actual Expenditures | Actual Expenditures
2016-10-01 | 2977730.4442 | 2977730.4442 | 0 | 0
2017-01-01 | 2977730.4442 | 5955460.8884 | 24702 | 24702
2017-04-01 | 2977730.4442 | 8933191.3326 | 218770 | 243472
2017-07-01 | 2977730.4442 | 11910921.7768 | 1194228 | 1437700
2017-10-01 | 2977730.4442 | 14888652.221 | 1666396 | 3104096
2018-01-01 | 2977730.4442 | 17866382.6652 | 2164402 | 5268498
2018-04-01 | 2977730.4442 | 20844113.1094 | 3498531 | 8767029
2018-07-01 | 2977730.4442 | 23821843.5536 | 2778053 | 11545082
2018-10-01 | 2977730.4442 | 26799573.9978 | 3710069 | 15255151
2019-01-01 | 2977730.4442 | 29777304.442 | 2114102 | 17369253
2019-04-01 | 2977730.4442 | 32755034.8862 | 2305244 | 19674497
2019-07-01 | 2977730.4442 | 35732765.3304 | 2831446 | 22505943
2019-10-01 | 2977730.4442 | 38710495.7746 | 4269054 | 26774997
2020-01-01 | 2977730.4442 | 41688226.2188 | 4587842 | 31362839
2020-04-01 | 2977730.4442 | 44665956.663 | 3481695 | 34844534
2020-07-01 | 2977730.4442 | 47643687.1072 | 2909306 | 37753840
2020-10-01 | 2977730.4442 | 50621417.5514 | 6197037 | 43950877
2021-01-01 | 2977730.4442 | 53599147.9957 | 7180138 | 51131015
2021-04-01 | 2977730.4442 | 56576878.4399 | 2096799 | 53227814
2021-07-01 | 2977730.4442 | 59554608.8841 | 2996910 | 56224724
2021-10-01 | 2885990.4442 | 62440599.3283 | 1585792 | 57810516
2022-01-01 | 2885990.4442 | 65326589.7725 | 4808988 | 62619504
2022-04-01 | 2885990.4442 | 68212580.2167 | 1648935 | 64268439
2022-07-01 | 1471246.1833 | 69683826.4 | 2300256 | 66568695
2022-10-01 | 617511.6 | 70301338 | 2383467 | 68952162 | BALANCE
2023-01-01 | 0 | 70301338 | 1434409 | 70386571 | -85233
Planning and Admin | Quarterly Expenditures | Projected Expenditures | Quarterly Actual Expenditures | Actual Expenditures
2016-10-01 | 614041.5975 | 614041.5975 | 0 | 0
2017-01-01 | 614041.5975 | 1228083.1949 | 338833 | 338833
2017-04-01 | 614041.5975 | 1842124.7924 | 1097622 | 1436455
2017-07-01 | 614041.5975 | 2456166.3898 | 1181098 | 2617553
2017-10-01 | 614041.5975 | 3070207.9873 | 937667 | 3555220
2018-01-01 | 614041.5975 | 3684249.5847 | 957223 | 4512443
2018-04-01 | 614041.5975 | 4298291.1822 | 1283832 | 5796275
2018-07-01 | 614041.5975 | 4912332.7796 | 949709 | 6745984
2018-10-01 | 614041.5975 | 5526374.3771 | 839311 | 7585295
2019-01-01 | 614041.5975 | 6140415.9745 | 871914 | 8457209
2019-04-01 | 614041.5975 | 6754457.572 | 792919 | 9250128
2019-07-01 | 614041.5975 | 7368499.1694 | 544957 | 9795085
2019-10-01 | 614041.5975 | 7982540.7669 | 830528 | 10625613
2020-01-01 | 614041.5975 | 8596582.3643 | 532610 | 11158223
2020-04-01 | 614041.5975 | 9210623.9618 | 592154 | 11750377
2020-07-01 | 614041.5975 | 9824665.5593 | 233749 | 11984126
2020-10-01 | 614041.5975 | 10438707.1567 | 342496 | 12326622
2021-01-01 | 614041.5975 | 11052748.7542 | 711416 | 13038038
2021-04-01 | 614041.5975 | 11666790.3516 | 327592 | 13365630
2021-07-01 | 614041.5975 | 12280831.9491 | 448453 | 13814083
2021-10-01 | 612588.2975 | 12893420.2465 | 153682 | 13967765
2022-01-01 | 601874.0117 | 13495294.2583 | 312438 | 14280203
2022-04-01 | 601874.0117 | 14097168.27 | 112286 | 14392489
2022-07-01 | 540710.49 | 14637878.76 | 217346 | 14609835
2022-10-01 | 967825.24 | 15605704 | 256756.46 | 14866591.46 | BALANCE
2023-01-01 | 0 | 15605704 | 154707.13 | 15021298.59 | 584405.41
Total Grant | Quarterly Expenditures | Projected Expenditures | Quarterly Actual Expenditures | Actual Expenditures
2016-10-01 | 3944988.346 | 3944988.346 | 0 | 0
2017-01-01 | 3944988.346 | 7889976.692 | 363535 | 363535
2017-04-01 | 3944988.346 | 11834965.038 | 1316392 | 1679927
2017-07-01 | 3944988.346 | 15779953.384 | 2375326 | 4055253
2017-10-01 | 3944988.346 | 19724941.73 | 2604063 | 6659316
2018-01-01 | 3944988.346 | 23669930.076 | 3121625 | 9780941
2018-04-01 | 3944988.346 | 27614918.422 | 5021869 | 14802810
2018-07-01 | 3944988.346 | 31559906.768 | 3892906 | 18695716
2018-10-01 | 3944988.346 | 35504895.114 | 5170594 | 23866310
2019-01-01 | 3944988.346 | 39449883.46 | 2986016 | 26852326
2019-04-01 | 3944988.346 | 43394871.806 | 3805616 | 30657942
2019-07-01 | 3944988.346 | 47339860.152 | 3836736 | 34494678
2019-10-01 | 3944988.346 | 51284848.4981 | 6347184 | 40841862
2020-01-01 | 3944988.346 | 55229836.8441 | 5784440 | 46626302
2020-04-01 | 3944988.346 | 59174825.1901 | 4581498 | 51207800
2020-07-01 | 3944988.346 | 63119813.5361 | 3143055 | 54350855
2020-10-01 | 3944988.346 | 67064801.8821 | 7090205 | 61441060
2021-01-01 | 3944988.346 | 71009790.2281 | 8344591 | 69785651
2021-04-01 | 3944988.346 | 74954778.5741 | 2651160 | 72436811
2021-07-01 | 3944988.346 | 78899766.9201 | 4344951 | 76781762
2021-10-01 | 3851795.046 | 82751561.9661 | 1739474 | 78521236
2022-01-01 | 3841080.7603 | 86592642.7264 | 5707269 | 84228505
2022-04-01 | 3841080.7603 | 90433723.4867 | 1919153 | 86147658
2022-07-01 | 2011956.6733 | 92445680.16 | 3154847 | 89302505
2022-10-01 | 1585336.84 | 94031017 | 2640223.46 | 91942728.46 | BALANCE
2023-01-01 | 0 | 94031017 | 1589116.13 | 93531844.59 | 499172.41

## Quarterly Projections
Quarterly Projections
| Housing: 971, 733, 734 | Non-Housing: 55, 69, 173 | Planning: 172 | Admin: 181 | Total Activities:
2016-10-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2017-01-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2017-04-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2017-07-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2017-10-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2018-01-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2018-04-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2018-07-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2018-10-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2019-01-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2019-04-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2019-07-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2019-10-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2020-01-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2020-04-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2020-07-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2020-10-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2021-01-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2021-04-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2021-07-01 | 353216.3043 | 2977730.4442 | 538699.1553 | 75342.4422 | 3944988.346
2021-10-01 | 353216.3043 | 2885990.4442 | 538699.1553 | 73889.1422 | 3851795.046
2022-01-01 | 353216.3043 | 2885990.4442 | 527984.8696 | 73889.1422 | 3841080.7603
2022-04-01 | 353216.3043 | 2885990.4442 | 527984.8696 | 73889.1422 | 3841080.7603
2022-07-01 | 0 | 1471246.1833 | 498713 | 41997.49 | 2011956.6733
2022-10-01 | 0 | 617511.6 | 473713 | 494112.24 | 1585336.84
2023-01-01 | 0 | 0 | 0 | 0 | 0
Total: | 8123975 | 70301338 | 13341078 | 2264626 | 94031017

## Actual Totals
Quarterly Projections
| Housing: 971, 733, 734 | Non-Housing: 55, 69, 173 | Planning: 172 | Admin: 181 | Total Activities:
2016-10-01 | 0 | 0 | 0 | 0 | 0
2017-01-01 | 0 | 24702 | 155816 | 183017 | 363535
2017-04-01 | 0 | 218770 | 963712 | 133910 | 1316392
2017-07-01 | 0 | 1194228 | 1096799 | 84299 | 2375326
2017-10-01 | 0 | 1666396 | 824135 | 113532 | 2604063
2018-01-01 | 0 | 2164402 | 905744 | 51479 | 3121625
2018-04-01 | 239506 | 3498531 | 1144422 | 139410 | 5021869
2018-07-01 | 165144 | 2778053 | 870730 | 78979 | 3892906
2018-10-01 | 621214 | 3710069 | 766333 | 72978 | 5170594
2019-01-01 | 0 | 2114102 | 802064 | 69850 | 2986016
2019-04-01 | 707453 | 2305244 | 721560 | 71359 | 3805616
2019-07-01 | 460333 | 2831446 | 492281 | 52676 | 3836736
2019-10-01 | 1247602 | 4269054 | 745676 | 84852 | 6347184
2020-01-01 | 663988 | 4587842 | 446348 | 86262 | 5784440
2020-04-01 | 507649 | 3481695 | 505897 | 86257 | 4581498
2020-07-01 | 0 | 2909306 | 184655 | 49094 | 3143055
2020-10-01 | 550672 | 6197037 | 276847 | 65649 | 7090205
2021-01-01 | 453037 | 7180138 | 603786 | 107630 | 8344591
2021-04-01 | 226769 | 2096799 | 293494 | 34098 | 2651160
2021-07-01 | 899588 | 2996910 | 384777 | 63676 | 4344951
2021-10-01 | 0 | 1585792 | 141689 | 11993 | 1739474
2022-01-01 | 585843 | 4808988 | 283753 | 28685 | 5707269
2022-04-01 | 157932 | 1648935 | 87095 | 25191 | 1919153
2022-07-01 | 637245 | 2300256 | 207037 | 10309 | 3154847
2022-10-01 | 0 | 2383467 | 223752.46 | 33004 | 2640223.46
2023-01-01 | 0 | 1434409 | 132384.13 | 22323 | 1589116.13
Total: | 8123975 | 70386571 | 13260786.59 | 1760512 | 93531844.59

## Dubuque Housing
DUBUQUE BEE BRANCH HEALTHY HOMES RESILIENCY PROGRAM
Activity Center |  |  |  | Activity 733 - Single Family Rental |  |  |  | Activity 734 - Multi-Family Rental |  |  |  | Activity 971 - Housing Repair & Rehab LMI |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities | [5 empty] | Total Units
Year | Quarter | Start Date | End Date | Quarter Projection | Cumulative Paid Projection | Actual Quarter Paid | Actual Total Paid | Quarter Projection | Cumulative Paid Projection | Actual Quarter Paid | Actual Total Paid | Quarter Projection | Cumulative Paid Projection | Actual Quarter Paid | Actual Total Paid | Quarter Projection | Cumulative Paid Projection | Actual Quarter Paid | Actual Total Paid | Quarter Projection | Cumulative Paid Projection | Actual Quarter Paid | Actual Total Paid | Actual Quarter Paid | Actual Cumulative & Paid
Year | Quarter | Start Date | End Date | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column202 | Column21 | Column22
1 | 1 | 2016-10-01 | 2016-12-31 | 51349.0435 | 51349.0435 | 0 | 0 | 142057.0435 | 142057.0435 | 0 | 0 | 159810.2174 | 159810.2174 | 0 | 0 | 20541.3478 | 20541.3478 | 0 | 0 | 373757.6522 | 373757.6522 | 0 | 0 | 0% | 0% | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 51349.0435 | 102698.087 | 0 | 0 | 142057.0435 | 284114.087 | 0 | 0 | 159810.2174 | 319620.4348 | 0 | 0 | 20541.3478 | 41082.6957 | 94291 | 94291 | 373757.6522 | 747515.3043 | 94291 | 94291 | 25.23% | 12.61% | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 51349.0435 | 154047.1304 | 0 | 0 | 142057.0435 | 426171.1304 | 0 | 0 | 159810.2174 | 479430.6522 | 0 | 0 | 20541.3478 | 61624.0435 | 92662 | 186953 | 373757.6522 | 1121272.9565 | 92662 | 186953 | 24.79% | 16.67% | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 51349.0435 | 205396.1739 | 0 | 0 | 142057.0435 | 568228.1739 | 0 | 0 | 159810.2174 | 639240.8696 | 0 | 0 | 20541.3478 | 82165.3913 | 17652 | 204605 | 373757.6522 | 1495030.6087 | 17652 | 204605 | 4.723% | 13.69% | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 51349.0435 | 256745.2174 | 0 | 0 | 142057.0435 | 710285.2174 | 0 | 0 | 159810.2174 | 799051.087 | 0 | 0 | 20541.3478 | 102706.7391 | 66699 | 271304 | 373757.6522 | 1868788.2609 | 66699 | 271304 | 17.85% | 14.52% | 5
2 | 2 | 2018-01-01 | 2018-03-31 | 51349.0435 | 308094.2609 | 0 | 0 | 142057.0435 | 852342.2609 | 0 | 0 | 159810.2174 | 958861.3043 | 0 | 0 | 20541.3478 | 123248.087 | 9864 | 281168 | 373757.6522 | 2242545.913 | 9864 | 281168 | 2.639% | 12.54% | 10
2 | 3 | 2018-04-01 | 2018-06-30 | 51349.0435 | 359443.3043 | 0 | 0 | 142057.0435 | 994399.3043 | 0 | 0 | 159810.2174 | 1118671.5217 | 239506 | 239506 | 20541.3478 | 143789.4348 | 61583 | 342751 | 373757.6522 | 2616303.5652 | 301089 | 582257 | 80.56% | 22.25% | 19
2 | 4 | 2018-07-01 | 2018-09-30 | 51349.0435 | 410792.3478 | 20990 | 20990 | 142057.0435 | 1136456.3478 | 71659 | 71659 | 159810.2174 | 1278481.7391 | 72495 | 312001 | 20541.3478 | 164330.7826 | 34922 | 377673 | 373757.6522 | 2990061.2174 | 200066 | 782323 | 53.53% | 26.16% | 9
3 | 1 | 2018-10-01 | 2018-12-31 | 51349.0435 | 462141.3913 | 170177 | 191167 | 142057.0435 | 1278513.3913 | 130339 | 201998 | 159810.2174 | 1438291.9565 | 320698 | 632699 | 20541.3478 | 184872.1304 | 26792 | 404465 | 373757.6522 | 3363818.8696 | 648006 | 1430329 | 173.4% | 42.52% | 11
3 | 2 | 2019-01-01 | 2019-03-31 | 51349.0435 | 513490.4348 | 0 | 191167 | 142057.0435 | 1420570.4348 | 0 | 201998 | 159810.2174 | 1598102.1739 | 0 | 632699 | 20541.3478 | 205413.4783 | 32671 | 437136 | 373757.6522 | 3737576.5217 | 32671 | 1463000 | 8.741% | 39.14% | 6
3 | 3 | 2019-04-01 | 2019-06-30 | 51349.0435 | 564839.4783 | 50554 | 241721 | 142057.0435 | 1562627.4783 | 88627 | 290625 | 159810.2174 | 1757912.3913 | 568272 | 1200971 | 20541.3478 | 225954.8261 | 14609 | 451745 | 373757.6522 | 4111334.1739 | 722062 | 2185062 | 193.2% | 53.15% | 8
3 | 4 | 2019-07-07 | 2019-09-30 | 51349.0435 | 616188.5217 | 4121 | 245842 | 142057.0435 | 1704684.5217 | 206774 | 497399 | 159810.2174 | 1917722.6087 | 249438 | 1450409 | 20541.3478 | 246496.1739 | 1391 | 453136 | 373757.6522 | 4485091.8261 | 461724 | 2646786 | 123.5% | 59.01% | 51
4 | 1 | 2019-10-01 | 2019-12-31 | 51349.0435 | 667537.5652 | 200531 | 446373 | 142057.0435 | 1846741.5652 | 570148 | 1067547 | 159810.2174 | 2077532.8261 | 476923 | 1927332 | 20541.3478 | 267037.5217 | 0 | 453136 | 373757.6522 | 4858849.4783 | 1247602 | 3894388 | 333.8% | 80.15% | 78
4 | 2 | 2020-01-01 | 2020-03-31 | 51349.0435 | 718886.6087 | 82671 | 529044 | 142057.0435 | 1988798.6087 | 446274 | 1513821 | 159810.2174 | 2237343.0435 | 135043 | 2062375 | 20541.3478 | 287578.8696 | 5214 | 458350 | 373757.6522 | 5232607.1304 | 669202 | 4563590 | 179% | 87.21% | 2
4 | 3 | 2020-04-01 | 2020-06-30 | 51349.0435 | 770235.6522 | 49599 | 578643 | 142057.0435 | 2130855.6522 | 398151 | 1911972 | 159810.2174 | 2397153.2609 | 59899 | 2122274 | 20541.3478 | 308120.2174 | 1529 | 459879 | 373757.6522 | 5606364.7826 | 509178 | 5072768 | 136.2% | 90.48% | 16
4 | 4 | 2020-07-01 | 2020-09-30 | 51349.0435 | 821584.6957 | 0 | 578643 | 142057.0435 | 2272912.6957 | 0 | 1911972 | 159810.2174 | 2556963.4783 | 0 | 2122274 | 20541.3478 | 328661.5652 | 0 | 459879 | 373757.6522 | 5980122.4348 | 0 | 5072768 | 0% | 84.83% | 10
5 | 1 | 2020-10-01 | 2020-12-31 | 51349.0435 | 872933.7391 | 158003 | 736646 | 142057.0435 | 2414969.7391 | 215183 | 2127155 | 159810.2174 | 2716773.6957 | 177486 | 2299760 | 20541.3478 | 349202.913 | 810 | 460689 | 373757.6522 | 6353880.087 | 551482 | 5624250 | 147.6% | 88.52% | 11
5 | 2 | 2021-01-01 | 2021-03-31 | 51349.0435 | 924282.7826 | 130130 | 866776 | 142057.0435 | 2557026.7826 | 56232 | 2183387 | 159810.2174 | 2876583.913 | 266675 | 2566435 | 20541.3478 | 369744.2609 | 1597 | 462286 | 373757.6522 | 6727637.7391 | 454634 | 6078884 | 121.6% | 90.36% | 8
5 | 3 | 2021-04-01 | 2021-06-30 | 51349.0435 | 975631.8261 | 64085 | 930861 | 142057.0435 | 2699083.8261 | 64991 | 2248378 | 159810.2174 | 3036394.1304 | 97693 | 2664128 | 20541.3478 | 390285.6087 | 1049 | 463335 | 373757.6522 | 7101395.3913 | 227818 | 6306702 | 60.95% | 88.81% | 6
5 | 4 | 2021-07-01 | 2021-09-30 | 51349.0435 | 1026980.8696 | 211069 | 1141930 | 142057.0435 | 2841140.8696 | 340688 | 2589066 | 159810.2174 | 3196204.3478 | 347831 | 3011959 | 20541.3478 | 410826.9565 | 5294 | 468629 | 373757.6522 | 7475153.0435 | 904882 | 7211584 | 242.1% | 96.47% | 14
6 | 1 | 2021-10-01 | 2021-12-31 | 51349.0435 | 1078329.913 | 0 | 1141930 | 142057.0435 | 2983197.913 | 0 | 2589066 | 159810.2174 | 3356014.5652 | 0 | 3011959 | 20541.3478 | 431368.3043 | 0 | 468629 | 373757.6522 | 7848910.6957 | 0 | 7211584 | 0% | 91.88% | 8
6 | 2 | 2022-01-01 | 2022-03-31 | 51349.0435 | 1129678.9565 | 25257 | 1167187 | 142057.0435 | 3125254.9565 | 219159 | 2808225 | 159810.2174 | 3515824.7826 | 341427 | 3353386 | 20541.3478 | 451909.6522 | 1244 | 469873 | 373757.6522 | 8222668.3478 | 587087 | 7798671 | 157.1% | 94.84% | 3
6 | 3 | 2022-04-01 | 2022-06-30 | 51349.0435 | 1181028 | 13841 | 1181028 | 142057.0435 | 3267312 | 0 | 2808225 | 159810.2174 | 3675635 | 144091 | 3497477 | 20541.3478 | 472451 | 918 | 470791 | 373757.6522 | 8596426 | 158850 | 7957521 | 42.5% | 92.57% | 36
6 | 4 | 2022-07-01 | 2022-09-30 |  | 1181028 | 0 | 1172082 |  | 3267312 | 459087 | 3267312 |  | 3675635 | 178158 | 3623577 |  | 472451 | 1660 | 472451 | 0 | 8596426 | 638905 | 8596426 |  | 100% | 0
|  |  |  | 1181028 | TOTAL | BALANCE | 8946 | 3267312 | TOTAL | BALANCE | 0 | 3675635 | TOTAL | BALANCE | 52058 | 472451 | TOTAL | BALANCE | 0 | 8596426 | TOTAL | BALANCE | 0 |  |  | 311
Closed | 2022-06-30
60 days expire August 30, 2022

## Benton
BENTON COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection2 | Cumulative $ Paid Projection3 | Actual Quarter $ Paid4 | Actual Total $ Paid5 | Quarter $ Projection6 | Cumulative $ Paid Projection7 | Actual Quarter $ Paid8 | Actual Total $ Paid9 | Quarter $ Projection10 | Cumulative $ Paid Projection11 | Actual Quarter $ Paid12 | Actual Total $ Paid13 | Actual Cumulative % Paid | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 13043.4783 | 13043.4783 | 0 | 0 | 443977.0833 | 443977.0833 | 0 | 0 | 8879.5417 | 8879.5417 | 0 | 0 | 474047.125 | 474047.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 13043.4783 | 26086.9565 | 0 | 0 | 443977.0833 | 887954.1667 | 0 | 0 | 8879.5417 | 17759.0833 | 3274 | 3274 | 474047.125 | 948094.25 | 3274 | 3274 | 0.34532 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 13043.4783 | 39130.4348 | 0 | 0 | 443977.0833 | 1331931.25 | 52762 | 52762 | 8879.5417 | 26638.625 | 7496 | 10770 | 474047.125 | 1422141.375 | 60258 | 63532 | 4.4673 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 13043.4783 | 52173.913 | 0 | 0 | 443977.0833 | 1775908.3333 | 113348 | 166110 | 8879.5417 | 35518.1667 | 7394 | 18164 | 474047.125 | 1896188.5 | 120742 | 184274 | 9.7181 | 7.9048 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 13043.4783 | 65217.3913 | 13151 | 13151 | 443977.0833 | 2219885.4167 | 59262 | 225372 | 8879.5417 | 44397.7083 | 11440 | 29604 | 474047.125 | 2370235.625 | 83853 | 268127 | 11.3123 | 7.9048 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 13043.4783 | 78260.8696 | 41583 | 54734 | 443977.0833 | 2663862.5 | 62726 | 288098 | 8879.5417 | 53277.25 | 10556 | 40160 | 474047.125 | 2844282.75 | 114865 | 382992 | 13.4653 | 7.9048 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 13043.4783 | 91304.3478 | 41583 | 96317 | 443977.0833 | 3107839.5833 | 68032 | 356130 | 8879.5417 | 62156.7917 | 8324 | 48484 | 474047.125 | 3318329.875 | 117939 | 500931 | 15.0959 | 7.9048 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 13043.4783 | 104347.8261 | 41583 | 137900 | 443977.0833 | 3551816.6667 | 143799 | 499929 | 8879.5417 | 71036.3333 | 11021 | 59505 | 474047.125 | 3792377 | 196403 | 697334 | 18.3878 | 7.9048 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 13043.4783 | 117391.3043 | 55444 | 193344 | 443977.0833 | 3995793.75 | 260423 | 760352 | 8879.5417 | 79915.875 | 13997 | 73502 | 474047.125 | 4266424.125 | 329864 | 1027198 | 24.0763 | 7.9048 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 13043.4783 | 130434.7826 | 41651 | 234995 | 443977.0833 | 4439770.8333 | 226886 | 987238 | 8879.5417 | 88795.4167 | 8603 | 82105 | 474047.125 | 4740471.25 | 277140 | 1304338 | 27.5149 | 7.9048 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 13043.4783 | 143478.2609 | 0 | 234995 | 443977.0833 | 4883747.9167 | 434995 | 1422233 | 8879.5417 | 97674.9583 | 18241 | 100346 | 474047.125 | 5214518.375 | 453236 | 1757574 | 33.7054 | 7.9048 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 13043.4783 | 156521.7391 | 13861 | 248856 | 443977.0833 | 5327725 | 399932 | 1822165 | 8879.5417 | 106554.5 | 16973 | 117319 | 474047.125 | 5688565.5 | 430766 | 2188340 | 38.4691 | 7.9048 | 0 | 0 | 0
4 | 1 | 2019-10-01 | 2019-12-31 | 13043.4783 | 169565.2174 | 23861 | 272717 | 443977.0833 | 5771702.0833 | 1212167 | 3034332 | 8879.5417 | 115434.0417 | 22275 | 139594 | 474047.125 | 6162612.625 | 1258303 | 3446643 | 55.9283 | 7.9048 | 0 | 0 | 0
4 | 2 | 2020-01-01 | 2020-03-31 | 13043.4783 | 182608.6957 | 0 | 272717 | 443977.0833 | 6215679.1667 | 783661 | 3817993 | 8879.5417 | 124313.5833 | 19206 | 158800 | 474047.125 | 6636659.75 | 802867 | 4249510 | 64.0309 | 7.9048 | 0 | 0 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 13043.4783 | 195652.1739 | 5000 | 277717 | 443977.0833 | 6659656.25 | 499917 | 4317910 | 8879.5417 | 133193.125 | 10835 | 169635 | 474047.125 | 7110706.875 | 515752 | 4765262 | 67.0153 | 7.9048 | 13 | 1 | 1
4 | 4 | 2020-07-01 | 2020-09-30 | 13043.4783 | 208695.6522 | 13861 | 291578 | 443977.0833 | 7103633.3333 | 830765 | 5148675 | 8879.5417 | 142072.6667 | 9440 | 179075 | 474047.125 | 7584754 | 854066 | 5619328 | 74.0871 | 7.9048 | 70 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 13043.4783 | 221739.1304 | 0 | 291578 | 443977.0833 | 7547610.4167 | 1549504 | 6698179 | 8879.5417 | 150952.2083 | 9021 | 188096 | 474047.125 | 8058801.125 | 1558525 | 7177853 | 89.0685 | 7.9048 | 0 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 13043.4783 | 234782.6087 | 0 | 291578 | 443977.0833 | 7991587.5 | 1245093 | 7943272 | 8879.5417 | 159831.75 | 5580 | 193676 | 474047.125 | 8532848.25 | 1250673 | 8428526 | 98.7774 | 7.9048 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 13043.4783 | 247826.087 | 0 | 291578 | 443977.0833 | 8435564.5833 | 666670 | 8609942 | 8879.5417 | 168711.2917 | 2325 | 196001 | 474047.125 | 9006895.375 | 668995 | 9097521 | 101.0062 | 7.9048 | 1 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 13043.4783 | 260869.5652 | 0 | 291578 | 443977.0833 | 8879541.6667 | 112397 | 8722339 | 8879.5417 | 177590.8333 | 2790 | 198791 | 474047.125 | 9480942.5 | 115187 | 9212708 | 97.1708 | 7.9048 | 5 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 13043.4783 | 273913.0435 | 0 | 291578 | 443977.0833 | 9323518.75 | 349450 | 9071789 | 8879.5417 | 186470.375 | 6045 | 204836 | 474047.125 | 9954989.625 | 355495 | 9568203 | 96.1146 | 7.9048 | 12 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 13043.4783 | 286956.5217 | 0 | 291578 | 443977.0833 | 9767495.8333 | 1088830 | 10160619 | 8879.5417 | 195349.9167 | 3999 | 208835 | 474047.125 | 10429036.75 | 1092829 | 10661032 | 102.2245 | 7.9048 | 0 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 13043.4783 | 300000 | 0 | 291578 | 443977.0833 | 10211472.9167 | 353233 | 10513852 | 8879.5417 | 204229.4583 | 3813 | 212648 | 474047.125 | 10903083.875 | 357046 | 11018078 | 101.0547 | 7.9048 | 12 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 12500 | 312500 | 0 | 291578 | 443977.0833 | 10655450 | 110101 | 10623953 | 8879.5417 | 213109 |  | 212648 | 474047.125 | 11377131 | 110101 | 11128179 | 97.8118 | 7.9048 | 0 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 |  |  | 8422 | 300000 |  |  | 200069 | 10824022 |  |  | 461 | 213109 | 0 | 11377131 | 208952 | 11337131 | 99.6484 |  |  | 0 | 0
7 | 2 | 2023-01-01 | 2023-03-31 | [12 empty] | 0 |  | 0
|  |  |  | 300000 | TOTAL | BALANCE | 0 | 10824022 | TOTAL | BALANCE | 0 | 213109 | TOTAL | BALANCE | 0 | 11377131 | TOTAL | BALANCE | 40000 |  | 166 | 113 | 1 | 1
|  | Closed | 2022-09-30
60 days expires November 30, 2022

## Buena Vista
BUENA VISTA COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Actual Cumulative % paid | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 8695.6522 | 8695.6522 | 0 | 0 | 93191.1739 | 93191.1739 | 0 | 0 | 2979.6522 | 2979.6522 |  | 0 | 104866.4783 | 104866.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 8695.6522 | 17391.3043 | 0 | 0 | 93191.1739 | 186382.3478 | 0 | 0 | 2979.6522 | 5959.3043 | 0 | 0 | 104866.4783 | 209732.9565 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 8695.6522 | 26086.9565 | 0 | 0 | 93191.1739 | 279573.5217 | 0 | 0 | 2979.6522 | 8938.9565 | 0 | 0 | 104866.4783 | 314599.4348 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 8695.6522 | 34782.6087 | 0 | 0 | 93191.1739 | 372764.6957 | 67896 | 67896 | 2979.6522 | 11918.6087 | 11577 | 11577 | 104866.4783 | 419465.913 | 79473 | 79473 | 18.9462 | 2.95 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 8695.6522 | 43478.2609 | 0 | 0 | 93191.1739 | 465955.8696 | 29893 | 97789 | 2979.6522 | 14898.2609 | 2084 | 13661 | 104866.4783 | 524332.3913 | 31977 | 111450 | 21.2556 | 2.95 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 8695.6522 | 52173.913 | 0 | 0 | 93191.1739 | 559147.0435 | 34698 | 132487 | 2979.6522 | 17877.913 | 1964 | 15625 | 104866.4783 | 629198.8696 | 36662 | 148112 | 23.5398 | 2.95 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 8695.6522 | 60869.5652 | 0 | 0 | 93191.1739 | 652338.2174 | 46398 | 178885 | 2979.6522 | 20857.5652 | 0 | 15625 | 104866.4783 | 734065.3478 | 46398 | 194510 | 26.4976 | 2.95 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 8695.6522 | 69565.2174 | 0 | 0 | 93191.1739 | 745529.3913 | 10196 | 189081 | 2979.6522 | 23837.2174 | 0 | 15625 | 104866.4783 | 838931.8261 | 10196 | 204706 | 24.4008 | 2.95 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 8695.6522 | 78260.8696 | 0 | 0 | 93191.1739 | 838720.5652 | 24468 | 213549 | 2979.6522 | 26816.8696 | 7649 | 23274 | 104866.4783 | 943798.3043 | 32117 | 236823 | 25.0925 | 2.95 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 8695.6522 | 86956.5217 | 14169 | 14169 | 93191.1739 | 931911.7391 | 62843 | 276392 | 2979.6522 | 29796.5217 | 0 | 23274 | 104866.4783 | 1048664.7826 | 77012 | 313835 | 29.9271 | 2.95 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 8695.6522 | 95652.1739 | 12745 | 26914 | 93191.1739 | 1025102.913 | 37306 | 313698 | 2979.6522 | 32776.1739 | 5033 | 28307 | 104866.4783 | 1153531.2609 | 55084 | 368919 | 31.9817 | 2.95 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 8695.6522 | 104347.8261 | 98648 | 125562 | 93191.1739 | 1118294.087 | 115313 | 429011 | 2979.6522 | 35755.8261 | 4131 | 32438 | 104866.4783 | 1258397.7391 | 218092 | 587011 | 46.6475 | 2.95 | 0 | 0 | 0
4 | 1 | 2019-10-01 | 2019-12-31 | 8695.6522 | 113043.4783 | 51017 | 176579 | 93191.1739 | 1211485.2609 | 61273 | 490284 | 2979.6522 | 38735.4783 | 0 | 32438 | 104866.4783 | 1363264.2174 | 112290 | 699301 | 51.2961 | 2.95 | 0 | 0 | 0
4 | 2 | 2020-01-01 | 2020-03-31 | 8695.6522 | 121739.1304 | 22158 | 198737 | 93191.1739 | 1304676.4348 | 182118 | 672402 | 2979.6522 | 41715.1304 | 14759 | 47197 | 104866.4783 | 1468130.6957 | 219035 | 918336 | 62.5514 | 2.95 | 0 | 0 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 8695.6522 | 130434.7826 | 0 | 198737 | 93191.1739 | 1397867.6087 | 91027 | 763429 | 2979.6522 | 44694.7826 | 8025 | 55222 | 104866.4783 | 1572997.1739 | 99052 | 1017388 | 64.6783 | 2.95 | 0 | 1 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 8695.6522 | 139130.4348 | 0 | 198737 | 93191.1739 | 1491058.7826 | 84499 | 847928 | 2979.6522 | 47674.4348 | 0 | 55222 | 104866.4783 | 1677863.6522 | 84499 | 1101887 | 65.672 | 2.95 | 0 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 8695.6522 | 147826.087 | 1263 | 200000 | 93191.1739 | 1584249.9565 | 36471 | 884399 | 2979.6522 | 50654.087 | 0 | 55222 | 104866.4783 | 1782730.1304 | 37734 | 1139621 | 63.9256 | 2.95 | 0 | 0 | 1
5 | 2 | 2021-01-01 | 2021-03-31 | 8695.6522 | 156521.7391 | 0 | 200000 | 93191.1739 | 1677441.1304 | 55116 | 939515 | 2979.6522 | 53633.7391 | 13310 | 68532 | 104866.4783 | 1887596.6087 | 68426 | 1208047 | 63.9992 | 2.95 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 8695.6522 | 165217.3913 | 0 | 200000 | 93191.1739 | 1770632.3043 | 42541 | 982056 | 2979.6522 | 56613.3913 | 0 | 68532 | 104866.4783 | 1992463.087 | 42541 | 1250588 | 62.7659 | 2.95 | 0 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 8695.6522 | 173913.0435 | 0 | 200000 | 93191.1739 | 1863823.4783 | 9716 | 991772 | 2979.6522 | 59593.0435 | 0 | 68532 | 104866.4783 | 2097329.5652 | 9716 | 1260304 | 60.0909 | 2.95 | 0 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 8695.6522 | 182608.6957 | 0 | 200000 | 93191.1739 | 1957014.6522 | 30738 | 1022510 | 2979.6522 | 62572.6957 | 0 | 68532 | 104866.4783 | 2202196.0435 | 30738 | 1291042 | 58.6252 | 2.95 | 0 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 8695.6522 | 191304.3478 | 0 | 200000 | 93191.1739 | 2050205.8261 | 1783 | 1024293 | 2979.6522 | 65552.3478 | 0 | 68532 | 104866.4783 | 2307062.5217 | 1783 | 1292825 | 56.0377 | 2.95 | 0 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 8695.6522 | 200000 | 0 | 200000 | 93191.1739 | 2143397 | 230384 | 1254677 | 2979.6522 | 68532 | 0 | 68532 | 104866.4783 | 2411929 | 230384 | 1523209 | 63.1531 | 2.95 | 4 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 |  | 200000 | 0 | 0 |  | 2143397 | 888720 | 2143397 |  | 68532 | 0 | 68532 | 0 | 2411929 | 888720 | 2411929 | 100
7 | 1 | 2022-10-01 | 2022-12-31
7 | 2 | 2023-01-01 | 2023-03-31
|  |  |  | 200000 | TOTAL | BALANCE | 8.7311e-11 | 2143397 | TOTAL | BALANCE | 0 | 68532 | TOTAL | BALANCE | -2.9104e-11 | 2411929 | TOTAL | BALANCE | -4.6566e-10 |  | 59 | 4 | 1 | 1
|  | Closed | 2022-06-30
60 Days Expires August 30, 2022

## Fremont
FREMONT COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Actual Cumulative % Paid | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33
1 | 1 | 2016-10-01 | 2016-12-31 | 8695.6522 | 8695.6522 | 0 | 0 | 86367.6957 | 86367.6957 | 0 | 0 | 1400.3913 | 1400.3913 | 0 | 0 | 96463.7391 | 96463.7391 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 8695.6522 | 17391.3043 | 0 | 0 | 86367.6957 | 172735.3913 | 0 | 0 | 1400.3913 | 2800.7826 | 0 | 0 | 96463.7391 | 192927.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 8695.6522 | 26086.9565 | 0 | 0 | 86367.6957 | 259103.087 | 0 | 0 | 1400.3913 | 4201.1739 | 0 | 0 | 96463.7391 | 289391.2174 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 8695.6522 | 34782.6087 | 0 | 0 | 86367.6957 | 345470.7826 | 50913 | 50913 | 1400.3913 | 5601.5652 | 0 | 0 | 96463.7391 | 385854.9565 | 50913 | 50913 | 13.1949 | 1.6 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 8695.6522 | 43478.2609 | 0 | 0 | 86367.6957 | 431838.4783 | 5833 | 56746 | 1400.3913 | 7001.9565 | 0 |  | 96463.7391 | 482318.6957 | 5833 | 56746 | 11.7652 | 1.6 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 8695.6522 | 52173.913 | 35 | 35 | 86367.6957 | 518206.1739 | 2155 | 58901 | 1400.3913 | 8402.3478 | 2697 | 2697 | 96463.7391 | 578782.4348 | 4887 | 61633 | 10.6487 | 1.6 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 8695.6522 | 60869.5652 | 31677 | 31712 | 86367.6957 | 604573.8696 | 14188 | 73089 | 1400.3913 | 9802.7391 | 6421 | 9118 | 96463.7391 | 675246.1739 | 52286 | 113919 | 16.8707 | 1.6 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 8695.6522 | 69565.2174 | 22543 | 54255 | 86367.6957 | 690941.5652 | 309 | 73398 | 1400.3913 | 11203.1304 | 0 | 9118 | 96463.7391 | 771709.913 | 22852 | 136771 | 17.7231 | 1.6 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 8695.6522 | 78260.8696 | 53988 | 108243 | 86367.6957 | 777309.2609 | 11822 | 85220 | 1400.3913 | 12603.5217 | 0 | 9118 | 96463.7391 | 868173.6522 | 65810 | 202581 | 23.3342 | 1.6 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 8695.6522 | 86956.5217 | 65019 | 173262 | 86367.6957 | 863676.9565 | 18965 | 104185 | 1400.3913 | 14003.913 | 496 | 9614 | 96463.7391 | 964637.3913 | 84480 | 287061 | 29.7584 | 1.6 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 8695.6522 | 95652.1739 | 12687 | 185949 | 86367.6957 | 950044.6522 | 25002 | 129187 | 1400.3913 | 15404.3043 | 2010 | 11624 | 96463.7391 | 1061101.1304 | 39699 | 326760 | 30.7944 | 1.6 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 8695.6522 | 104347.8261 | 9577 | 195526 | 86367.6957 | 1036412.3478 | 27357 | 156544 | 1400.3913 | 16804.6957 | 0 | 11624 | 96463.7391 | 1157564.8696 | 36934 | 363694 | 31.4189 | 1.6 | 0 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 8695.6522 | 113043.4783 | 4474 | 200000 | 86367.6957 | 1122780.0435 | 58547 | 215091 | 1400.3913 | 18205.087 | 4574 | 16198 | 96463.7391 | 1254028.6087 | 67595 | 431289 | 34.3923 | 1.6 | 0 | 0 | 0
4 | 2 | 2020-01-01 | 2020-03-31 | 8695.6522 | 121739.1304 | 0 | 200000 | 86367.6957 | 1209147.7391 | 32649 | 247740 | 1400.3913 | 19605.4783 | 1022 | 17220 | 96463.7391 | 1350492.3478 | 33671 | 464960 | 34.4289 | 1.6 | 0 | 1 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 8695.6522 | 130434.7826 | 0 | 200000 | 86367.6957 | 1295515.4348 | 19573 | 267313 | 1400.3913 | 21005.8696 | 0 | 17220 | 96463.7391 | 1446956.087 | 19573 | 484533 | 33.4864 | 1.6 | 0 | 0 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 8695.6522 | 139130.4348 | 0 | 200000 | 86367.6957 | 1381883.1304 | 64968 | 332281 | 1400.3913 | 22406.2609 | 1943 | 19163 | 96463.7391 | 1543419.8261 | 66911 | 551444 | 35.7287 | 1.6 | 0 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 8695.6522 | 147826.087 | 0 | 200000 | 86367.6957 | 1468250.8261 | 146883 | 479164 | 1400.3913 | 23806.6522 | 0 | 19163 | 96463.7391 | 1639883.5652 | 146883 | 698327 | 42.5839 | 1.6 | 0 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 8695.6522 | 156521.7391 | 0 | 200000 | 86367.6957 | 1554618.5217 | 52554 | 531718 | 1400.3913 | 25207.0435 | 721 | 19884 | 96463.7391 | 1736347.3043 | 53275 | 751602 | 43.2864 | 1.6 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 8695.6522 | 165217.3913 | 0 | 200000 | 86367.6957 | 1640986.2174 | 71690 | 603408 | 1400.3913 | 26607.4348 | 2529 | 22413 | 96463.7391 | 1832811.0435 | 74219 | 825821 | 45.0576 | 1.6 | 0 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 8695.6522 | 173913.0435 | 0 | 200000 | 86367.6957 | 1727353.913 | 196819 | 800227 | 1400.3913 | 28007.8261 | 0 | 22413 | 96463.7391 | 1929274.7826 | 196819 | 1022640 | 53.0064 | 1.6 | 1 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 8695.6522 | 182608.6957 | 0 | 200000 | 86367.6957 | 1813721.6087 | 301620 | 1101847 | 1400.3913 | 29408.2174 | 1646 | 24059 | 96463.7391 | 2025738.5217 | 303266 | 1325906 | 65.453 | 1.6 | 10 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 8695.6522 | 191304.3478 | 0 | 200000 | 86367.6957 | 1900089.3043 | 555352 | 1657199 | 1400.3913 | 30808.6087 | 3352 | 27411 | 96463.7391 | 2122202.2609 | 558704 | 1884610 | 88.8044 | 1.6 | 0 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 8695.6522 | 200000 | 0 | 200000 | 86367.6957 | 1986457 | 0 | 1657199 | 1400.3913 | 32209 | 0 | 27411 | 96463.7391 | 2218666 | 0 | 1884610 | 84.9434 | 1.6 | 56 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 |  | 200000 |  | 200000 |  | 1986457 | 314791 | 1971990 |  | 32209 | 4798 | 32209 | 0 | 2218666 | 319589 | 2204199 | 99.3479
7 | 1 | 2022-10-01 | 2022-12-31
7 | 2 | 2023-01-01 | 2023-03-31
|  |  |  | 200000 | TOTAL | BALANCE | 0 | 1971990 | TOTAL | BALANCE | 0 | 32209 | TOTAL | BALANCE | 2.1828e-11 | 2218666 | TOTAL | BALANCE | 14467 |  | 32 | 67 | 1 | 1
|  | Closed | 2022-06-30
60 days expires August 30, 2022

## Howard
HOWARD COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Actual Cumulative % Paid | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column13 | Column14 | Column15 | Column16 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37
1 | 1 | 2016-10-01 | 2016-12-31 | 9782.6087 | 9782.6087 | 0 | 0 | 153955.1739 | 153955.1739 | 0 | 0 | 2940.5217 | 2940.5217 | 0 | 0 | 153307.1667 | 153307.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 9782.6087 | 19565.2174 | 0 | 0 | 153955.1739 | 307910.3478 | 0 | 0 | 2940.5217 | 5881.0435 | 0 | 0 | 153307.1667 | 306614.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 9782.6087 | 29347.8261 | 0 | 0 | 153955.1739 | 461865.5217 | 0 | 0 | 2940.5217 | 8821.5652 | 0 | 0 | 153307.1667 | 459921.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 9782.6087 | 39130.4348 | 65000 | 65000 | 153955.1739 | 615820.6957 | 92243 | 92243 | 2940.5217 | 11762.087 | 8901 | 8901 | 153307.1667 | 613228.6667 | 166144 | 166144 | 27.0933 | 3.95 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 9782.6087 | 48913.0435 | 0 | 65000 | 153955.1739 | 769775.8696 | 20583 | 112826 | 2940.5217 | 14702.6087 | 0 | 8901 | 153307.1667 | 766535.8333 | 20583 | 186727 | 24.3599 | 3.95 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 9782.6087 | 58695.6522 | 40000 | 105000 | 153955.1739 | 923731.0435 | 27384 | 140210 | 2940.5217 | 17643.1304 | 3455 | 12356 | 153307.1667 | 919843 | 70839 | 257566 | 28.0011 | 3.95 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 9782.6087 | 68478.2609 | 40000 | 145000 | 153955.1739 | 1077686.2174 | 28290 | 168500 | 2940.5217 | 20583.6522 | 2825 | 15181 | 153307.1667 | 1073150.1667 | 71115 | 328681 | 30.6277 | 3.95 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 9782.6087 | 78260.8696 | 40000 | 185000 | 153955.1739 | 1231641.3913 | 21337 | 189837 | 2940.5217 | 23524.1739 | 3242 | 18423 | 153307.1667 | 1226457.3333 | 64579 | 393260 | 32.0647 | 3.95 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 9782.6087 | 88043.4783 | 0 | 185000 | 153955.1739 | 1385596.5652 | 32764 | 222601 | 2940.5217 | 26464.6957 | 2887 | 21310 | 153307.1667 | 1379764.5 | 35651 | 428911 | 31.0858 | 3.95 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 9782.6087 | 97826.087 | 0 | 185000 | 153955.1739 | 1539551.7391 | 131801 | 354402 | 2940.5217 | 29405.2174 | 4515 | 25825 | 153307.1667 | 1533071.6667 | 136316 | 565227 | 36.8689 | 3.95 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 9782.6087 | 107608.6957 | 0 | 185000 | 153955.1739 | 1693506.913 | 64464 | 418866 | 2940.5217 | 32345.7391 | 2785 | 28610 | 153307.1667 | 1686378.8333 | 67249 | 632476 | 37.505 | 3.95 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 9782.6087 | 117391.3043 | 0 | 185000 | 153955.1739 | 1847462.087 | 84475 | 503341 | 2940.5217 | 35286.2609 | 3359 | 31969 | 153307.1667 | 1839686 | 87834 | 720310 | 39.154 | 3.95 | 0 | 0 | 0
4 | 1 | 2019-10-01 | 2019-12-31 | 9782.6087 | 127173.913 | 40000 | 225000 | 153955.1739 | 2001417.2609 | 181868 | 685209 | 2940.5217 | 38226.7826 | 5390 | 37359 | 153307.1667 | 1992993.1667 | 227258 | 947568 | 47.545 | 3.95 | 0 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 9782.6087 | 136956.5217 | 0 | 225000 | 153955.1739 | 2155372.4348 | 69981 | 755190 | 2940.5217 | 41167.3043 | 0 | 37359 | 153307.1667 | 2146300.3333 | 69981 | 1017549 | 47.4094 | 3.95 | 0 | 1 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 9782.6087 | 146739.1304 | 0 | 225000 | 153955.1739 | 2309327.6087 | 68075 | 823265 | 2940.5217 | 44107.8261 | 3721 | 41080 | 153307.1667 | 2299607.5 | 71796 | 1089345 | 47.3709 | 3.95 | 1 | 0 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 9782.6087 | 156521.7391 | 0 | 225000 | 153955.1739 | 2463282.7826 | 55165 | 878430 | 2940.5217 | 47048.3478 | 5737 | 46817 | 153307.1667 | 2452914.6667 | 60902 | 1150247 | 46.8931 | 3.95 | 1 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 9782.6087 | 166304.3478 | 0 | 225000 | 153955.1739 | 2617237.9565 | 110691 | 989121 | 2940.5217 | 49988.8696 | 3513 | 50330 | 153307.1667 | 2606221.8333 | 114204 | 1264451 | 48.5166 | 3.95 | 4 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 9782.6087 | 176086.9565 | 0 | 225000 | 153955.1739 | 2771193.1304 | 306088 | 1295209 | 2940.5217 | 52929.3913 | 7697 | 58027 | 153307.1667 | 2759529 | 313785 | 1578236 | 57.1922 | 3.95 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 9782.6087 | 185869.5652 | 0 | 225000 | 153955.1739 | 2925148.3043 | 0 | 1295209 | 2940.5217 | 55869.913 | 0 | 58027 | 153307.1667 | 2912836.1667 | 0 | 1578236 | 54.1821 | 3.95 | 3 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 9782.6087 | 195652.1739 | 0 | 225000 | 153955.1739 | 3079103.4783 | 642135 | 1937344 | 2940.5217 | 58810.4348 | 6467 | 64494 | 153307.1667 | 3066143.3333 | 648602 | 2226838 | 72.6267 | 3.95 | 9 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 9782.6087 | 205434.7826 | 0 | 225000 | 153955.1739 | 3233058.6522 | 0 | 1937344 | 2940.5217 | 61750.9565 | 0 | 64494 | 153307.1667 | 3219450.5 | 0 | 2226838 | 69.1683 | 3.95 | 6 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 9782.6087 | 215217.3913 | 0 | 225000 | 153955.1739 | 3387013.8261 | 963455 | 2900799 | 2940.5217 | 64691.4783 | 3138 | 67632 | 153307.1667 | 3372757.6667 | 966593 | 3193431 | 94.6831 | 3.95 | 0 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 9782.6087 | 225000 | 0 | 225000 | 153955.1739 | 3540969 | 0 | 2900799 | 2940.5217 | 67632 | 0 | 67632 | 153307.1667 | 3526064.8333 | 0 | 3193431 | 90.5664 | 3.95 | 4 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 |  | 225000 | 0 | 225000 |  | 3540969 | 0 | 2900799 | 2818 | 70450 | 0 | 67632 | 153307.1667 | 3679372 | 0 | 3193431 | 86.7928
7 | 1 | 2022-10-01 | 2022-12-31 | [6 empty] | 476634 | 3377433 |  |  | 9307 | 76939 |  | 3679372 |  | 3193431 | 86.7928
7 | 2 | 2023-01-01 | 2023-03-31
|  |  |  | 225000 | TOTAL | BALANCE | -1.1642e-10 | 3377433 | TOTAL | BALANCE | 0 | 76939 | TOTAL | BALANCE | 0 | 3679372 | TOTAL | BALANCE | 485941 |  | 79 | 28 | 1 | 1
|  | Closed | 2022-06-30

## Iowa
IOWA COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Actual Cumulative % Paid | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column13 | Column14 | Column15 | Column16 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37
1 | 1 | 2016-10-01 | 2016-12-31 | 4166.6667 | 4166.6667 | 0 | 0 | 215775.0833 | 215775.0833 | 0 | 0 | 4398.3333 | 4398.3333 | 0 | 0 | 209813.7083 | 209813.7083 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 4166.6667 | 8333.3333 | 0 | 0 | 215775.0833 | 431550.1667 | 258 | 258 | 4398.3333 | 8796.6667 | 3568 | 3568 | 209813.7083 | 419627.4167 | 3826 | 3826 | 0.91176 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 4166.6667 | 12500 | 0 | 0 | 215775.0833 | 647325.25 | 52 | 310 | 4398.3333 | 13195 | 3190 | 6758 | 209813.7083 | 629441.125 | 3242 | 7068 | 1.1229 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 4166.6667 | 16666.6667 | 6146 | 6146 | 215775.0833 | 863100.3333 | 66942 | 67252 | 4398.3333 | 17593.3333 | 5395 | 12153 | 209813.7083 | 839254.8333 | 78483 | 85551 | 10.1937 | 4.85 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 4166.6667 | 20833.3333 | 9912 | 16058 | 215775.0833 | 1078875.4167 | 21591 | 88843 | 4398.3333 | 21991.6667 | 3581 | 15734 | 209813.7083 | 1049068.5417 | 35084 | 120635 | 11.4992 | 4.85 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 4166.6667 | 25000 | 15623 | 31681 | 215775.0833 | 1294650.5 | 46308 | 135151 | 4398.3333 | 26390 | 3162 | 18896 | 209813.7083 | 1258882.25 | 65093 | 185728 | 14.7534 | 4.85 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 4166.6667 | 29166.6667 | 28676 | 60357 | 215775.0833 | 1510425.5833 | 144874 | 280025 | 4398.3333 | 30788.3333 | 13532 | 32428 | 209813.7083 | 1468695.9583 | 187082 | 372810 | 25.3837 | 4.85 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 4166.6667 | 33333.3333 | 12312 | 72669 | 215775.0833 | 1726200.6667 | 31213 | 311238 | 4398.3333 | 35186.6667 | 4418 | 36846 | 209813.7083 | 1678509.6667 | 47943 | 420753 | 25.0671 | 4.85 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 4166.6667 | 37500 | 9888 | 82557 | 215775.0833 | 1941975.75 | 70031 | 381269 | 4398.3333 | 39585 | 4837 | 41683 | 209813.7083 | 1888323.375 | 84756 | 505509 | 26.7703 | 4.85 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 4166.6667 | 41666.6667 | 13053 | 95610 | 215775.0833 | 2157750.8333 | 121985 | 503254 | 4398.3333 | 43983.3333 | 3558 | 45241 | 209813.7083 | 2098137.0833 | 138596 | 644105 | 30.6989 | 4.85 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 4166.6667 | 45833.3333 | 2914 | 98524 | 215775.0833 | 2373525.9167 | 124202 | 627456 | 4398.3333 | 48381.6667 | 3952 | 49193 | 209813.7083 | 2307950.7917 | 131068 | 775173 | 33.5871 | 4.85 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 4166.6667 | 50000 | 1333 | 99857 | 215775.0833 | 2589301 | 65624 | 693080 | 4398.3333 | 52780 | 6417 | 55610 | 209813.7083 | 2517764.5 | 73374 | 848547 | 33.7024 | 4.85 | 0 | 0 | 0
4 | 1 | 2019-10-01 | 2019-12-31 | 4166.6667 | 54166.6667 | 143 | 100000 | 215775.0833 | 2805076.0833 | 483504 | 1176584 | 4398.3333 | 57178.3333 | 16695 | 72305 | 209813.7083 | 2727578.2083 | 500342 | 1348889 | 49.4537 | 4.85 | 50 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 4166.6667 | 58333.3333 | 0 | 100000 | 215775.0833 | 3020851.1667 | 251407 | 1427991 | 4398.3333 | 61576.6667 | 12602 | 84907 | 209813.7083 | 2937391.9167 | 264009 | 1612898 | 54.9092 | 4.85 | 0 | 1 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 4166.6667 | 62500 | 0 | 100000 | 215775.0833 | 3236626.25 | 463155 | 1891146 | 4398.3333 | 65975 | 9068 | 93975 | 209813.7083 | 3147205.625 | 472223 | 2085121 | 66.2531 | 4.85 | 61 | 0 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 4166.6667 | 66666.6667 | 0 | 100000 | 215775.0833 | 3452401.3333 | 280591 | 2171737 | 4398.3333 | 70373.3333 | 5348 | 99323 | 209813.7083 | 3357019.3333 | 285939 | 2371060 | 70.6299 | 4.85 | 0 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 4166.6667 | 70833.3333 | 0 | 100000 | 215775.0833 | 3668176.4167 | 435263 | 2607000 | 4398.3333 | 74771.6667 | 5580 | 104903 | 209813.7083 | 3566833.0417 | 440843 | 2811903 | 78.8347 | 4.85 | 0 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 4166.6667 | 75000 | 0 | 100000 | 215775.0833 | 3883951.5 | 463291 | 3070291 | 4398.3333 | 79170 | 651 | 105554 | 209813.7083 | 3776646.75 | 463942 | 3275845 | 86.7395 | 4.85 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 4166.6667 | 79166.6667 | 0 | 100000 | 215775.0833 | 4099726.5833 | 282642 | 3352933 | 4398.3333 | 83568.3333 | 0 | 105554 | 209813.7083 | 3986460.4583 | 282642 | 3558487 | 89.2643 | 4.85 | 0 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 4166.6667 | 83333.3333 | 0 | 100000 | 215775.0833 | 4315501.6667 | 459915 | 3812848 | 4398.3333 | 87966.6667 | 6 | 105560 | 209813.7083 | 4196274.1667 | 459921 | 4018408 | 95.7613 | 4.85 | 62 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 4166.6667 | 87500 | 0 | 100000 | 215775.0833 | 4531276.75 | 58648 | 3871496 | 4398.3333 | 92365 | 0 | 105560 | 209813.7083 | 4406087.875 | 58648 | 4077056 | 92.5323 | 4.85 | 0 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 4166.6667 | 91666.6667 | 0 | 100000 | 215775.0833 | 4747051.8333 | 0 | 3871496 | 4398.3333 | 96763.3333 | 0 | 105560 | 209813.7083 | 4615901.5833 | 0 | 4077056 | 88.3263 | 4.85 | 123 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 4166.6667 | 95833.3333 | 0 | 100000 | 215775.0833 | 4962826.9167 | 786216 | 4657712 | 4398.3333 | 101161.6667 | 0 | 105560 | 209813.7083 | 4825715.2917 | 786216 | 4863272 | 100.7783 | 4.85 | 67 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 4166.6667 | 100000 | 0 | 100000 | 215775.0833 | 5178602 | 93013 | 4750725 | 4398.3333 | 105560 | 0 | 105560 | 209813.7083 | 5035529 | 93013 | 4956285 | 98.4263 |  |  | 0 | 0
Column1: 7; Column2: 1; Column3: 2022-10-01; Column4: 2022-12-31; Column15: 79244; Column16: 4829969; Column34: 5035529; Column35: 79244; Column36: 5035529; Column37: 100 |  |  | 0 | 0
7 | 2 | 2023-01-01 | 2023-03-31
|  |  |  | 100000 | TOTAL | BALANCE | 2.9104e-11 | 4829969 | TOTAL | BALANCE | 0 | 105560 | TOTAL | BALANCE | -2.9104e-11 | 5035529 | TOTAL | BALANCE | 79244 |  | 97 | 363 | 1 | 1
|  | Closed | 2022-06-30

## Johnson
JOHNSON COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 7000 | 7000 | 0 | 0 | 153231 | 153231 |  | 0 | 3088.68 | 3088.68 | 0 | 0 | 163319.68 | 163319.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 7000 | 14000 | 0 | 0 | 153231 | 306462 | 0 | 0 | 3088.68 | 6177.36 | 4576 | 4576 | 163319.68 | 326639.36 | 4576 | 4576 | 1.4009 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 7000 | 21000 | 0 | 0 | 153231 | 459693 | 1199 | 1199 | 3088.68 | 9266.04 | 8612 | 13188 | 163319.68 | 489959.04 | 9811 | 14387 | 2.9364 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 7000 | 28000 | 0 | 0 | 153231 | 612924 | 13031 | 14230 | 3088.68 | 12354.72 | 5237 | 18425 | 163319.68 | 653278.72 | 18268 | 32655 | 4.9986 | 3.2727 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 7000 | 35000 | 4371 | 4371 | 153231 | 766155 | 73698 | 87928 | 3088.68 | 15443.4 | 8417 | 26842 | 163319.68 | 816598.4 | 86486 | 119141 | 14.5899 | 3.2727 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 7000 | 42000 | 11344 | 15715 | 153231 | 919386 | 28941 | 116869 | 3088.68 | 18532.08 | 2930 | 29772 | 163319.68 | 979918.08 | 43215 | 162356 | 16.5683 | 3.2727 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 7000 | 49000 | 12548 | 28263 | 153231 | 1072617 | 29400 | 146269 | 3088.68 | 21620.76 | 12555 | 42327 | 163319.68 | 1143237.76 | 54503 | 216859 | 18.9688 | 3.2727 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 7000 | 56000 | 7347 | 35610 | 153231 | 1225848 | 77635 | 223904 | 3088.68 | 24709.44 | 10742 | 53069 | 163319.68 | 1306557.44 | 95724 | 312583 | 23.9242 | 3.2727 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 7000 | 63000 | 13334 | 48944 | 153231 | 1379079 | 63837 | 287741 | 3088.68 | 27798.12 | 2058 | 55127 | 163319.68 | 1469877.12 | 79229 | 391812 | 26.6561 | 3.2727 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 7000 | 70000 | 81513 | 130457 | 153231 | 1532310 | 141245 | 428986 | 3088.68 | 30886.8 | 33 | 55160 | 163319.68 | 1633196.8 | 222791 | 614603 | 37.6319 | 3.2727 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 7000 | 77000 | 43912 | 174369 | 153231 | 1685541 | 66792 | 495778 | 3088.68 | 33975.48 | 4165 | 59325 | 163319.68 | 1796516.48 | 114869 | 729472 | 40.6048 | 3.2727 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 7000 | 84000 | 628 | 174997 | 153231 | 1838772 | 95967 | 591745 | 3088.68 | 37064.16 | 6464 | 65789 | 163319.68 | 1959836.16 | 103059 | 832531 | 42.4796 | 3.2727 | 0 | 0 | 0
4 | 1 | 2019-10-01 | 2019-12-31 | 7000 | 91000 | 3 | 175000 | 153231 | 1992003 | 153936 | 745681 | 3088.68 | 40152.84 | 8045 | 73834 | 163319.68 | 2123155.84 | 161984 | 994515 | 46.8414 | 3.2727 | 0 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 7000 | 98000 | 0 | 175000 | 153231 | 2145234 | 82911 | 828592 | 3088.68 | 43241.52 | 977 | 74811 | 163319.68 | 2286475.52 | 83888 | 1078403 | 47.1644 | 3.2727 | 0 | 1 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 7000 | 105000 | 0 | 175000 | 153231 | 2298465 | 98182 | 926774 | 3088.68 | 46330.2 | 419 | 75230 | 163319.68 | 2449795.2 | 98601 | 1177004 | 48.045 | 3.2727 | 0 | 0 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 7000 | 112000 | 0 | 175000 | 153231 | 2451696 | 66396 | 993170 | 3088.68 | 49418.88 | 93 | 75323 | 163319.68 | 2613114.88 | 66489 | 1243493 | 47.5866 | 3.2727 | 0 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 7000 | 119000 | 0 | 175000 | 153231 | 2604927 | 450747 | 1443917 | 3088.68 | 52507.56 | 744 | 76067 | 163319.68 | 2776434.56 | 451491 | 1694984 | 61.0489 | 3.2727 | 2 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 7000 | 126000 | 0 | 175000 | 153231 | 2758158 | 148272 | 1592189 | 3088.68 | 55596.24 | 837 | 76904 | 163319.68 | 2939754.24 | 149109 | 1844093 | 62.7295 | 3.2727 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 7000 | 133000 | 0 | 175000 | 153231 | 2911389 | 95244 | 1687433 | 3088.68 | 58684.92 | 186 | 77090 | 163319.68 | 3103073.92 | 95430 | 1939523 | 62.5033 | 3.2727 | 20 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 7000 | 140000 | 0 | 175000 | 153231 | 3064620 | 35511 | 1722944 | 3088.68 | 61773.6 | 0 | 77090 | 163319.68 | 3266393.6 | 35511 | 1975034 | 60.4653 | 3.2727 | 0 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 7000 | 147000 | 0 | 175000 | 153231 | 3217851 | 287471 | 2010415 | 3088.68 | 64862.28 | 0 | 77090 | 163319.68 | 3429713.28 | 287471 | 2262505 | 65.9678 | 3.2727 | 13 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 7000 | 154000 | 0 | 175000 | 153231 | 3371082 | 201468 | 2211883 | 3088.68 | 67950.96 | 127 | 77217 | 163319.68 | 3593032.96 | 201595 | 2464100 | 68.5799 | 3.2727 | 0 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 7000 | 161000 | 0 | 175000 | 153231 | 3524313 | 160747 | 2372630 | 3088.68 | 71039.64 | 0 | 77217 | 163319.68 | 3756352.64 | 160747 | 2624847 | 69.8775 | 3.2727 | 0 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 7000 | 168000 | 0 | 175000 | 153231 | 3677544 | 614845 | 2987475 | 3088.68 | 74128.32 | 0 | 77217 | 163319.68 | 3919672.32 | 614845 | 3239692 | 82.6521 | 3.2727 | 0 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | 7000 | 175000 | 0 | 175000 | 153231 | 3830775 | 409559 | 3397034 | 3088.68 | 77217 | 0 | 77217 | 163319.68 | 4082992 | 409559 | 3649251 | 89.3769 | 3.2727
7 | 2 | 2023-01-01 | 2023-03-31 |  | 175000 | 0 | 175000 |  | 3830775 | 657852 | 4054886 |  | 77217 | 0 | 77217 | 0 | 4082992 | 657852 | 4307103 | 105.4889
|  |  |  | 175000 | TOTAL | BALANCE | -2.9104e-11 | 4054886 | TOTAL | BALANCE | 0 | 77217 | TOTAL | BALANCE | -2.9104e-11 | 4432126 | TOTAL | BALANCE | 1807279 |  | 72 | 35 | 1 | 1
|  | Closed | 2022-12-31
60 days expires March 2, 2023

## Mills
MILLS COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Quarter $ Projection | Cumulative $ paid Projection | Actual Quarter $ paid | Actual Total $ paid | Actual Cumulative % paid | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 8333.3333 | 8333.3333 | 0 | 0 | 193982.4167 | 193982.4167 | 0 | 0 | 4240.375 | 4240.375 | 0 | 0 | 207082.5 | 207082.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 8333.3333 | 16666.6667 | 0 | 0 | 193982.4167 | 387964.8333 | 0 | 0 | 4240.375 | 8480.75 | 0 | 0 | 207082.5 | 414165 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 8333.3333 | 25000 | 0 | 0 | 193982.4167 | 581947.25 | 0 | 0 | 4240.375 | 12721.125 | 0 | 0 | 207082.5 | 621247.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 8333.3333 | 33333.3333 | 96 | 96 | 193982.4167 | 775929.6667 | 0 | 0 | 4240.375 | 16961.5 | 0 | 0 | 207082.5 | 828330 | 96 | 96 | 0.01159 | 4.2857 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 8333.3333 | 41666.6667 | 0 | 96 | 193982.4167 | 969912.0833 | 122333 | 122333 | 4240.375 | 21201.875 | 6811 | 6811 | 207082.5 | 1035412.5 | 129144 | 129240 | 12.482 | 4.2857 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 8333.3333 | 50000 | 0 | 96 | 193982.4167 | 1163894.5 | 64872 | 187205 | 4240.375 | 25442.25 | 0 | 6811 | 207082.5 | 1242495 | 64872 | 194112 | 15.6228 | 4.2857 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 8333.3333 | 58333.3333 | 31677 | 31773 | 193982.4167 | 1357876.9167 | 33261 | 220466 | 4240.375 | 29682.625 | 8290 | 15101 | 207082.5 | 1449577.5 | 73228 | 267340 | 18.4426 | 4.2857 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 8333.3333 | 66666.6667 | 22543 | 54316 | 193982.4167 | 1551859.3333 | 46551 | 267017 | 4240.375 | 33923 | 0 | 15101 | 207082.5 | 1656660 | 69094 | 336434 | 20.308 | 4.2857 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 8333.3333 | 75000 | 71520 | 125836 | 193982.4167 | 1745841.75 | 53667 | 320684 | 4240.375 | 38163.375 | 4347 | 19448 | 207082.5 | 1863742.5 | 129534 | 465968 | 25.0017 | 4.2857 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 8333.3333 | 83333.3333 | 30554 | 156390 | 193982.4167 | 1939824.1667 | 40865 | 361549 | 4240.375 | 42403.75 | 2723 | 22171 | 207082.5 | 2070825 | 74142 | 540110 | 26.0819 | 4.2857 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 8333.3333 | 91666.6667 | 39195 | 195585 | 193982.4167 | 2133806.5833 | 148272 | 509821 | 4240.375 | 46644.125 | 0 | 22171 | 207082.5 | 2277907.5 | 187467 | 727577 | 31.9406 | 4.2857 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 8333.3333 | 100000 | 4340 | 199925 | 193982.4167 | 2327789 | 84228 | 594049 | 4240.375 | 50884.5 | 0 | 22171 | 207082.5 | 2484990 | 88568 | 816145 | 32.843 | 4.2857 | 0 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 8333.3333 | 108333.3333 | 75 | 200000 | 193982.4167 | 2521771.4167 | 133416 | 727465 | 4240.375 | 55124.875 | 9385 | 31556 | 207082.5 | 2692072.5 | 142876 | 959021 | 35.6239 | 4.2857 | 0 | 0 | 0
4 | 2 | 2020-01-01 | 2020-03-31 | 8333.3333 | 116666.6667 | 0 | 200000 | 193982.4167 | 2715753.8333 | 206618 | 934083 | 4240.375 | 59365.25 | 0 | 31556 | 207082.5 | 2899155 | 206618 | 1165639 | 40.2062 | 4.2857 | 0 | 1 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 8333.3333 | 125000 | 0 | 200000 | 193982.4167 | 2909736.25 | 232331 | 1166414 | 4240.375 | 63605.625 | 5661 | 37217 | 207082.5 | 3106237.5 | 237992 | 1403631 | 45.1875 | 4.2857 | 0 | 0 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 8333.3333 | 133333.3333 | 0 | 200000 | 193982.4167 | 3103718.6667 | 100906 | 1267320 | 4240.375 | 67846 | 0 | 37217 | 207082.5 | 3313320 | 100906 | 1504537 | 45.4087 | 4.2857 | 0 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 8333.3333 | 141666.6667 | 0 | 200000 | 193982.4167 | 3297701.0833 | 207369 | 1474689 | 4240.375 | 72086.375 | 19261 | 56478 | 207082.5 | 3520402.5 | 226630 | 1731167 | 49.1753 | 4.2857 | 0 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 8333.3333 | 150000 | 0 | 200000 | 193982.4167 | 3491683.5 | 1483270 | 2957959 | 4240.375 | 76326.75 | 0 | 56478 | 207082.5 | 3727485 | 1483270 | 3214437 | 86.2361 | 4.2857 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 8333.3333 | 158333.3333 | 0 | 200000 | 193982.4167 | 3685665.9167 | 146375 | 3104334 | 4240.375 | 80567.125 | 9914 | 66392 | 207082.5 | 3934567.5 | 156289 | 3370726 | 85.6695 | 4.2857 | 2 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 8333.3333 | 166666.6667 | 0 | 200000 | 193982.4167 | 3879648.3333 | 117627 | 3221961 | 4240.375 | 84807.5 | 24227 | 90619 | 207082.5 | 4141650 | 141854 | 3512580 | 84.8111 | 4.2857 | 0 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 8333.3333 | 175000 | 0 | 200000 | 193982.4167 | 4073630.75 | 142605 | 3364566 | 4240.375 | 89047.875 | 0 | 90619 | 207082.5 | 4348732.5 | 142605 | 3655185 | 84.0517 | 4.2857 | 29 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 8333.3333 | 183333.3333 | 0 | 200000 | 193982.4167 | 4267613.1667 | 706840 | 4071406 | 4240.375 | 93288.25 | 4300 | 94919 | 207082.5 | 4555815 | 711140 | 4366325 | 95.8407 | 4.2857 | 0 | 0 | 0
6 | 1 | 2022-04-01 | 2022-06-30 | 8333.3333 | 191666.6667 | 0 | 200000 | 193982.4167 | 4461595.5833 | 13176 | 4084582 | 4240.375 | 97528.625 | 1762 | 96681 | 207082.5 | 4762897.5 | 14938 | 4381263 | 91.9873 | 4.2857 | 5 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 8333.3333 | 200000 | 0 | 200000 | 193982.4167 | 4655578 | 278786 | 4363368 | 4240.375 | 101769 | 0 | 96681 | 207082.5 | 4969980 | 278786 | 4660049 | 93.7639 | 4.2857 | 0 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | [6 empty] | 304843 | 4668211 |  |  | 5088 | 101769 |  | 4969980 | 309931 | 4969980 | 100
8 | 1 | 2023-01-01 | 2023-03-31
|  |  |  | 200000 | TOTAL | BALANCE | 5.8208e-11 | 4668211 | TOTAL | BALANCE | 0 | 101769 | TOTAL | BALANCE | 0 | 4969980 | TOTAL | BALANCE | 0 |  | 90 | 36 | 1 | 1
|  | Closed | 2022-09-30
60 days expires November 30, 2022

## Winneshiek
WINNESHIEK COUNTY CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Watershed Plan |  |  |  | Activity 173 - Design & Construction |  |  |  | Activity 181 - Administration |  |  |  | Total All Activities
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Quarter $ Projection | Cumulative $ Paid Projection | Actual Quarter $ Paid | Actual Total $ Paid | Actual Cumulative % Paid | Watershed Practices Projected | Watershed Practices Completed | Plans Projected | Plans Completed
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column13 | Column14 | Column15 | Column16 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37
1 | 1 | 2016-10-01 | 2016-12-31 | 8000 | 8000 | 0 | 0 | 205290.6 | 205290.6 | 0 | 0 | 4276.56 | 4276.56 | 0 | 0 | 226246.36 | 226246.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 8000 | 16000 | 0 | 0 | 205290.6 | 410581.2 | 0 | 0 | 4276.56 | 8553.12 | 0 | 0 | 226246.36 | 452492.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 8000 | 24000 | 0 | 0 | 205290.6 | 615871.8 | 0 | 0 | 4276.56 | 12829.68 | 0 | 0 | 226246.36 | 678739.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 8000 | 32000 | 60000 | 60000 | 205290.6 | 821162.4 | 4974 | 4974 | 4276.56 | 17106.24 | 9031 | 9031 | 226246.36 | 904985.44 | 74005 | 74005 | 8.1775 | 4.6364 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 8000 | 40000 | 0 | 60000 | 205290.6 | 1026453 | 139634 | 144608 | 4276.56 | 21382.8 | 0 | 9031 | 226246.36 | 1131231.8 | 139634 | 213639 | 18.8855 | 4.6364 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 8000 | 48000 | 35000 | 95000 | 205290.6 | 1231743.6 | 43053 | 187661 | 4276.56 | 25659.36 | 4213 | 13244 | 226246.36 | 1357478.16 | 82266 | 295905 | 21.7981 | 4.6364 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 8000 | 56000 | 35000 | 130000 | 205290.6 | 1437034.2 | 26914 | 214575 | 4276.56 | 29935.92 | 3163 | 16407 | 226246.36 | 1583724.52 | 65077 | 360982 | 22.7932 | 4.6364 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 8000 | 64000 | 35000 | 165000 | 205290.6 | 1642324.8 | 58574 | 273149 | 4276.56 | 34212.48 | 4694 | 21101 | 226246.36 | 1809970.88 | 98268 | 459250 | 25.3733 | 4.6364 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 8000 | 72000 | 0 | 165000 | 205290.6 | 1847615.4 | 82449 | 355598 | 4276.56 | 38489.04 | 3793 | 24894 | 226246.36 | 2036217.24 | 86242 | 545492 | 26.7895 | 4.6364 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 8000 | 80000 | 0 | 165000 | 205290.6 | 2052906 | 104847 | 460445 | 4276.56 | 42765.6 | 7728 | 32622 | 226246.36 | 2262463.6 | 112575 | 658067 | 29.0863 | 4.6364 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 8000 | 88000 | 35000 | 200000 | 205290.6 | 2258196.6 | 112803 | 573248 | 4276.56 | 47042.16 | 7425 | 40047 | 226246.36 | 2488709.96 | 155228 | 813295 | 32.6794 | 4.6364 | 0 | 0 | 1
3 | 4 | 2019-07-07 | 2019-09-30 | 8000 | 96000 | 0 | 200000 | 205290.6 | 2463487.2 | 0 | 573248 | 4276.56 | 51318.72 | 0 | 40047 | 226246.36 | 2714956.32 | 0 | 813295 | 29.9561 | 4.6364 | 0 | 0 | 0
4 | 1 | 2019-10-01 | 2019-12-31 | 8000 | 104000 | 0 | 200000 | 205290.6 | 2668777.8 | 198617 | 771865 | 4276.56 | 55595.28 | 5961 | 46008 | 226246.36 | 2941202.68 | 204578 | 1017873 | 34.6074 | 4.6364 | 0 | 0 | 0
4 | 2 | 2020-01-01 | 2020-03-31 | 8000 | 112000 | 0 | 200000 | 205290.6 | 2874068.4 | 148966 | 920831 | 4276.56 | 59871.84 | 0 | 46008 | 226246.36 | 3167449.04 | 148966 | 1166839 | 36.8384 | 4.6364 | 0 | 1 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 8000 | 120000 | 0 | 200000 | 205290.6 | 3079359 | 40498 | 961329 | 4276.56 | 64148.4 | 5850 | 51858 | 226246.36 | 3393695.4 | 46348 | 1213187 | 35.7483 | 4.6364 | 0 | 0 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 8000 | 128000 | 0 | 200000 | 205290.6 | 3284649.6 | 147277 | 1108606 | 4276.56 | 68424.96 | 7443 | 59301 | 226246.36 | 3619941.76 | 154720 | 1367907 | 37.7881 | 4.6364 | 4 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 8000 | 136000 | 0 | 200000 | 205290.6 | 3489940.2 | 239395 | 1348001 | 4276.56 | 72701.52 | 5911 | 65212 | 226246.36 | 3846188.12 | 245306 | 1613213 | 41.9432 | 4.6364 | 6 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 8000 | 144000 | 0 | 200000 | 205290.6 | 3695230.8 | 806119 | 2154120 | 4276.56 | 76978.08 | 12188 | 77400 | 226246.36 | 4072434.48 | 818307 | 2431520 | 59.7068 | 4.6364 | 8 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 8000 | 152000 | 0 | 200000 | 205290.6 | 3900521.4 | 0 | 2154120 | 4276.56 | 81254.64 | 0 | 77400 | 226246.36 | 4298680.84 | 0 | 2431520 | 56.5643 | 4.6364 | 0 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 8000 | 160000 | 0 | 200000 | 205290.6 | 4105812 | 773767 | 2927887 | 4276.56 | 85531.2 | 8196 | 85596 | 226246.36 | 4524927.2 | 781963 | 3213483 | 71.0173 | 4.6364 | 0 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 8000 | 168000 | 0 | 200000 | 205290.6 | 4311102.6 | 0 | 2927887 | 4276.56 | 89807.76 | 0 | 85596 | 226246.36 | 4751173.56 | 0 | 3213483 | 67.6356 | 4.6364 | 11 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 8000 | 176000 | 0 | 200000 | 205290.6 | 4516393.2 | 1291260 | 4219147 | 4276.56 | 94084.32 | 4361 | 89957 | 226246.36 | 4977419.92 | 1295621 | 4509104 | 90.5912 | 4.6364 | 0 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 8000 | 184000 | 0 | 200000 | 205290.6 | 4721683.8 | 0 | 4219147 | 4276.56 | 98360.88 | 0 | 89957 | 226246.36 | 5203666.28 | 0 | 4509104 | 86.6524 | 4.6364 | 4 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 8000 | 192000 | 0 | 200000 | 205290.6 | 4926974.4 |  | 4219147 | 4276.56 | 102637.44 | 0 | 89957 | 226246.36 | 5429912.64 | 0 | 4509104 | 83.0419 | 4.6364 | 3 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | 8000 | 200000 | 0 | 200000 | 205290.6 | 5132265 | 913118 | 5132265 | 4276.56 | 106914 | 16957 | 106914 | 226246.36 | 5656159 | 930075 | 5439179 | 96.1638 | 4.6364
7 | 2 | 2023-01-01 | 2023-03-31 | [6 empty] | 216980 | 5349245 |  | 106914 |  | 106914 | 0 | 5656159 | 216980 | 5656159 | 100
|  |  |  | 200000 | TOTAL | BALANCE | 0 | 5349245 | TOTAL | BALANCE | 0 | 106914 | TOTAL | BALANCE | 0 | 5656159 | TOTAL | BALANCE | 216980 |  | 102 | 36 | 1 | 1
|  | Closed | 2022-10-31
60 Days Expires December 31, 2022

## Coralville Infra
Coralville CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 69 Storm Water Improvements |  |  |  |  | Activity 181 Admin
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Activity 69 Public Facilities Projected | Activity 69 Public Facilities Completed
2016 | 1 | 2016-10-01 | 2016-12-31 | 91740 | 91740 | 0 | 0 | 0 | 1453.3 | 1453.3 | 0 | 0 | 0% | 0 | 0
2017 | 1 | 2017-01-01 | 2017-03-31 | 91740 | 183480 | 24444 | 24444 | 13.3224 | 1453.3 | 2906.6 | 33620 | 33620 | 1157% | 0 | 0
2017 | 2 | 2017-04-01 | 2017-06-30 | 91740 | 275220 | 58367 | 82811 | 30.089 | 1453.3 | 4359.9 | -23622 | 9998 | 229.3% | 0 | 0
2017 | 3 | 2017-07-01 | 2017-09-30 | 91740 | 366960 | 2147 | 84958 | 23.1518 | 1453.3 | 5813.2 | 1907 | 11905 | 204.8% | 0 | 0
2017 | 4 | 2017-10-01 | 2017-12-31 | 91740 | 458700 | 116873 | 201831 | 44.0007 | 1453.3 | 7266.5 | 3628 | 15533 | 213.8% | 0 | 0
2018 | 1 | 2018-01-01 | 2018-03-31 | 91740 | 550440 | 525096 | 726927 | 132.0629 | 1453.3 | 8719.8 | 6278 | 21811 | 250.1% | 0 | 0
2018 | 2 | 2018-04-01 | 2018-06-30 | 91740 | 642180 | 1107873 | 1834800 | 285.7143 | 1453.3 | 10173.1 | 5813 | 27624 | 271.5% | 0 | 2
2018 | 3 | 2018-07-01 | 2018-09-30 | 91740 | 733920 | 0 | 1834800 | 250 | 1453.3 | 11626.4 | 1442 | 29066 | 250% | 0 | 0
2018 | 4 | 2018-10-01 | 2018-12-31 | 91740 | 825660 | 0 | 1834800 | 222.2222 | 1453.3 | 13079.7 | 0 | 29066 | 222.2% | 0 | 0
2019 | 1 | 2019-01-01 | 2019-03-31 | 91740 | 917400 | 0 | 1834800 | 200 | 1453.3 | 14533 | 0 | 29066 | 200% | 0 | 0
2019 | 2 | 2019-04-01 | 2019-06-30 | 91740 | 1009140 | 0 | 1834800 | 181.8182 | 1453.3 | 15986.3 | 0 | 29066 | 181.8% | 0 | 0
2019 | 3 | 2019-07-07 | 2019-09-30 | 91740 | 1100880 | 0 | 1834800 | 166.6667 | 1453.3 | 17439.6 | 0 | 29066 | 166.7% | 0 | 0
2019 | 4 | 2019-10-01 | 2019-12-31 | 91740 | 1192620 | 0 | 1834800 | 153.8462 | 1453.3 | 18892.9 | 0 | 29066 | 153.8% | 0 | 0
2020 | 1 | 2020-01-01 | 2020-03-31 | 91740 | 1284360 | 0 | 1834800 | 142.8571 | 1453.3 | 20346.2 | 0 | 29066 | 142.9% | 0 | 0
2020 | 2 | 2020-04-01 | 2020-06-30 | 91740 | 1376100 | 0 | 1834800 | 133.3333 | 1453.3 | 21799.5 | 0 | 29066 | 133.3% | 0 | 0
2020 | 3 | 2020-07-01 | 2020-09-30 | 91740 | 1467840 | 0 | 1834800 | 125 | 1453.3 | 23252.8 | 0 | 29066 | 125% | 0 | 0
2020 | 4 | 2020-10-01 | 2020-12-31 | 91740 | 1559580 | 0 | 1834800 | 117.6471 | 1453.3 | 24706.1 | 0 | 29066 | 117.6% | 0 | 0
2021 | 1 | 2021-01-01 | 2021-03-31 | 91740 | 1651320 | 0 | 1834800 | 111.1111 | 1453.3 | 26159.4 | 0 | 29066 | 111.1% | 0 | 0
2021 | 2 | 2021-04-01 | 2021-06-30 | 91740 | 1743060 | 0 | 1834800 | 105.2632 | 1453.3 | 27612.7 | 0 | 29066 | 105.3% | 0 | 0
2021 | 3 | 2021-07-01 | 2021-09-30 | 91740 | 1834800 | 0 | 1834800 | 100 | 1453.3 | 29066 | 0 | 29066 | 100% | 2 | 0
2021 | 4 | 2021-10-01 | 2021-12-31
2022 | 1 | 2022-01-01 | 2022-03-31
2022 | 2 | 2022-04-01 | 2022-06-30
2022 | 3 | 2022-07-01 | 2022-09-30
2022 | 4 | 2022-10-01 | 2022-12-31
2023 | 1 | 2023-01-01 | 2023-03-31
|  |  |  | 1834800 | TOTAL |  | 0 | BALANCE | 29066 | TOTAL | 29066 | 0 | BALANCE | 2 | 2

## Dubuque Infra
Dubuque CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 - Planning Pre App Costs |  |  |  |  | Activity 69 - Storm Sewer Improvements |  |  |  |  | Activity 181 - Admin
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Activity 69 Public Facilities Projected | Activity 69 Public Facilities Completed | Plans Proposed | Plans Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 1554.4783 | 1554.4783 | 0 | 0 | 0 | 1081230.2174 | 1081230.2174 | 0 | 0 | 0 | 6847.7391 | 6847.7391 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017 | 1 | 2017-01-01 | 2017-03-31 | 1554.4783 | 3108.9565 | 35753 | 35753 | 1150 | 1081230.2174 | 2162460.4348 | 0 | 0 | 0 | 6847.7391 | 13695.4783 | 11412 | 11412 | 83.3268 | 0 | 0 | 0 | 0
2017 | 2 | 2017-04-01 | 2017-06-30 | 1554.4783 | 4663.4348 | 0 | 35753 | 766.6667 | 1081230.2174 | 3243690.6522 | 90861 | 90861 | 2.8012 | 6847.7391 | 20543.2174 | 13889 | 25301 | 123.1599 | 0 | 0 | 1 | 1
2017 | 3 | 2017-07-01 | 2017-09-30 | 1554.4783 | 6217.913 | 0 | 35753 | 575 | 1081230.2174 | 4324920.8696 | 77942 | 168803 | 3.903 | 6847.7391 | 27390.9565 | 3988 | 29289 | 106.9295 | 0 | 0 | 0 | 0
2017 | 4 | 2017-10-01 | 2017-12-31 | 1554.4783 | 7772.3913 | 0 | 35753 | 460 | 1081230.2174 | 5406151.087 | 863358 | 1032161 | 19.0923 | 6847.7391 | 34238.6957 | 6465 | 35754 | 104.4257 | 0 | 0 | 0 | 0
2018 | 1 | 2018-01-01 | 2018-03-31 | 1554.4783 | 9326.8696 | 0 | 35753 | 383.3333 | 1081230.2174 | 6487381.3043 | 1039205 | 2071366 | 31.9292 | 6847.7391 | 41086.4348 | 3639 | 39393 | 95.8784 | 0 | 0 | 0 | 0
2018 | 2 | 2018-04-01 | 2018-06-30 | 1554.4783 | 10881.3478 | 0 | 35753 | 328.5714 | 1081230.2174 | 7568611.5217 | 1421960 | 3493326 | 46.1554 | 6847.7391 | 47934.1739 | 10756 | 50149 | 104.6206 | 0 | 0 | 0 | 0
2018 | 3 | 2018-07-01 | 2018-09-30 | 1554.4783 | 12435.8261 | 0 | 35753 | 287.5 | 1081230.2174 | 8649841.7391 | 2221985 | 5715311 | 66.0742 | 6847.7391 | 54781.913 | 7512 | 57661 | 105.2555 | 0 | 0 | 0 | 0
2018 | 4 | 2018-10-01 | 2018-12-31 | 1554.4783 | 13990.3043 | 0 | 35753 | 255.5556 | 1081230.2174 | 9731071.9565 | 2048483 | 7763794 | 79.7835 | 6847.7391 | 61629.6522 | 2941 | 60602 | 98.3325 | 0 | 0 | 0 | 0
2019 | 1 | 2019-01-01 | 2019-03-31 | 1554.4783 | 15544.7826 | 0 | 35753 | 230 | 1081230.2174 | 10812302.1739 | 680135 | 8443929 | 78.0956 | 6847.7391 | 68477.3913 | 3219 | 63821 | 93.2001 | 0 | 0 | 0 | 0
2019 | 2 | 2019-04-01 | 2019-06-30 | 1554.4783 | 17099.2609 | 0 | 35753 | 209.0909 | 1081230.2174 | 11893532.3913 | 1245653 | 9689582 | 81.4693 | 6847.7391 | 75325.1304 | 7219 | 71040 | 94.3112 | 0 | 0 | 0 | 0
2019 | 3 | 2019-07-07 | 2019-09-30 | 1554.4783 | 18653.7391 | 0 | 35753 | 191.6667 | 1081230.2174 | 12974762.6087 | 1824968 | 11514550 | 88.7457 | 6847.7391 | 82172.8696 | 10427 | 81467 | 99.141 | 0 | 0 | 0 | 0
2019 | 4 | 2019-10-01 | 2019-12-31 | 1554.4783 | 20208.2174 | 0 | 35753 | 176.9231 | 1081230.2174 | 14055992.8261 | 1757278 | 13271828 | 94.4211 | 6847.7391 | 89020.6087 | 3424 | 84891 | 95.3611 | 0 | 0 | 0 | 0
2020 | 1 | 2020-01-01 | 2020-03-31 | 1554.4783 | 21762.6957 | 0 | 35753 | 164.2857 | 1081230.2174 | 15137223.0435 | 2810969 | 16082797 | 106.2467 | 6847.7391 | 95868.3478 | 8627 | 93518 | 97.5484 | 0 | 0 | 0 | 0
2020 | 2 | 2020-04-01 | 2020-06-30 | 1554.4783 | 23317.1739 | 0 | 35753 | 153.3333 | 1081230.2174 | 16218453.2609 | 1763706 | 17846503 | 110.0383 | 6847.7391 | 102716.087 | 9951 | 103469 | 100.733 | 0 | 0 | 0 | 0
2020 | 3 | 2020-07-01 | 2020-09-30 | 1554.4783 | 24871.6522 | 0 | 35753 | 143.75 | 1081230.2174 | 17299683.4783 | 1079574 | 18926077 | 109.4013 | 6847.7391 | 109563.8261 | 3397 | 106866 | 97.5377 | 0 | 0 | 0 | 0
2020 | 4 | 2020-10-01 | 2020-12-31 | 1554.4783 | 26426.1304 | 0 | 35753 | 135.2941 | 1081230.2174 | 18380913.6957 | 1984135 | 20910212 | 113.7605 | 6847.7391 | 116411.5652 | 7220 | 114086 | 98.0023 | 0 | 0 | 0 | 0
2021 | 1 | 2021-01-01 | 2021-03-31 | 1554.4783 | 27980.6087 | 0 | 35753 | 127.7778 | 1081230.2174 | 19462143.913 | 2124424 | 23034636 | 118.3561 | 6847.7391 | 123259.3043 | 12623 | 126709 | 102.7987 | 0 | 0 | 0 | 0
2021 | 2 | 2021-04-01 | 2021-06-30 | 1554.4783 | 29535.087 | 0 | 35753 | 121.0526 | 1081230.2174 | 20543374.1304 | 664952 | 23699588 | 115.3637 | 6847.7391 | 130107.0435 | 4873 | 131582 | 101.1336 | 0 | 0 | 0 | 0
2021 | 3 | 2021-07-01 | 2021-09-30 | 1554.4783 | 31089.5652 | 0 | 35753 | 115 | 1081230.2174 | 21624604.3478 | 648268 | 24347856 | 112.5933 | 6847.7391 | 136954.7826 | 3783 | 135365 | 98.8392 | 0 | 0 | 0 | 0
2021 | 4 | 2021-10-01 | 2021-12-31 | 1554.4783 | 32644.0435 | 0 | 35753 | 109.5238 | 1081230.2174 | 22705834.5652 | 415260 | 24763116 | 109.0606 | 6847.7391 | 143802.5217 | 3435 | 138800 | 96.5213 | 0 | 0 | 0 | 0
2022 | 1 | 2022-01-01 | 2022-03-31 | 1554.4783 | 34198.5217 | 0 | 35753 | 104.5455 | 1081230.2174 | 23787064.7826 |  | 24763116 | 104.1033 | 6847.7391 | 150650.2609 | 0 | 138800 | 92.1339 | 0 | 0 | 0 | 0
2022 | 2 | 2022-04-01 | 2022-06-30 | 1554.4783 | 35753 | 0 | 35753 | 100 | 1081230.2174 | 24868295 | 105179 | 24868295 | 100 | 6847.7391 | 157498 | 18698 |  | 0 | 3 | 3 | 0 | 0
2022 | 3 | 2022-07-01 | 2022-09-30 |  |  | 0
2022 | 4 | 2022-10-01 | 2022-12-31
2023 | 1 | 2023-01-01 | 2023-03-31
|  |  |  | 35753 | TOTAL | 35753 | BALANCE | 0 | 24868295 | TOTAL | 24868295 | BALANCE | 0 | 157498 | TOTAL | 157498 | BALANCE | 0 | 3 | 3 | 1 | 1
|  | Closed | 2022-06-30
60 days expires August 30, 2022

## Storm Lake
Storm Lake CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 55- Sanitary Sewer Improvements |  |  |  |  | Activity 69 - Storm Water Improvements |  |  |  |  | Activity 181 - Admin
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Total $ Spent | Actual Cumulative % Spent | Activity 55 # Linear Feet Projected | Activity 55 # Linear Feet Completed | Activity 69 Public Facilities Projected | Activity 69 Public Facilities Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 53961.68 | 53961.68 | 0 | 0 | 0 | 205028.32 | 205028.32 | 0 | 0 | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 2017-01-01 | 2017-03-31 | 53961.68 | 107923.36 | 0 | 0 | 0 | 205028.32 | 410056.64 | 0 | 0 | 0 | 2400 | 4800 | 5925 | 5925 | 123.4375 | 0 | 0 | 0 | 0
1 | 3 | 2017-04-01 | 2017-06-30 | 53961.68 | 161885.04 | 9668 | 9668 | 5.9721 | 205028.32 | 615084.96 | 5861 | 5861 | 0.95288 | 2400 | 7200 | 2500 | 8425 | 117.0139 | 0 | 0 | 0 | 0
1 | 4 | 2017-07-01 | 2017-09-30 | 53961.68 | 215846.72 | 47700 | 57368 | 26.5781 | 205028.32 | 820113.28 | 657092 | 662953 | 80.8368 | 2400 | 9600 | 2500 | 10925 | 113.8021 | 0 | 0 | 0 | 0
2 | 1 | 2017-10-01 | 2017-12-31 | 53961.68 | 269808.4 | 11014 | 68382 | 71.5186 | 205028.32 | 1025141.6 | 202324 | 865277 | 84.4056 | 2400 | 12000 | 0 | 10925 | 91.0417 | 0 | 0 | 0 | 0
2 | 2 | 2018-01-01 | 2018-03-31 | 53961.68 | 323770.08 | 11160 | 79542 | 24.5674 | 205028.32 | 1230169.92 | 278804 | 1144081 | 93.0019 | 2400 | 14400 | 2500 | 13425 | 93.2292 | 0 | 0 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 53961.68 | 377731.76 | 138045 | 217587 | 57.6036 | 205028.32 | 1435198.24 | 439296 | 1583377 | 110.3246 | 2400 | 16800 | 5000 | 18425 | 109.6726 | 0 | 0 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 53961.68 | 431693.44 | 0 | 217587 | 50.4031 | 205028.32 | 1640226.56 | 166454 | 1749831 | 106.6823 | 2400 | 19200 | 0 | 18425 | 95.9635 | 0 | 0 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 53961.68 | 485655.12 | 489295 | 706882 | 145.5523 | 205028.32 | 1845254.88 | 572830 | 2322661 | 125.8721 | 2400 | 21600 | 2500 | 20925 | 96.875 | 0 | 0 | 0 | 0
3 | 2 | 2019-01-01 | 2019-03-31 | 53961.68 | 539616.8 | 94556 | 801438 | 148.5198 | 205028.32 | 2050283.2 | 489974 | 2812635 | 137.1828 | 2400 | 24000 | 5000 | 25925 | 108.0208 | 0 | 0 | 0 | 0
3 | 3 | 2019-04-01 | 2019-06-30 | 53961.68 | 593578.48 | 14834 | 816272 | 137.5171 | 205028.32 | 2255311.52 | 30921 | 2843556 | 126.0826 | 2400 | 26400 | 5000 | 30925 | 117.1402 | 0 | 0 | 0 | 0
3 | 4 | 2019-07-07 | 2019-09-30 | 53961.68 | 647540.16 | 24078 | 840350 | 129.7757 | 205028.32 | 2460339.84 | 109504 | 2953060 | 120.0265 | 2400 | 28800 | 2500 | 33425 | 116.059 | 0 | 0 | 0 | 0
4 | 1 | 2019-10-01 | 2019-12-31 | 53961.68 | 701501.84 | 3011 | 843361 | 120.2222 | 205028.32 | 2665368.16 | 25437 | 2978497 | 111.7481 | 2400 | 31200 | 5000 | 38425 | 123.1571 | 0 | 0 | 0 | 0
4 | 2 | 2020-01-01 | 2020-03-31 | 53961.68 | 755463.52 | 11700 | 855061 | 113.1836 | 205028.32 | 2870396.48 | 6862 | 2985359 | 104.0051 | 2400 | 33600 | 2500 | 40925 | 121.8006 | 0 | 0 | 0 | 0
4 | 3 | 2020-04-01 | 2020-06-30 | 53961.68 | 809425.2 | 49875 | 904936 | 111.7998 | 205028.32 | 3075424.8 | 155356 | 3140715 | 102.123 | 2400 | 36000 | 2500 | 43425 | 120.625 | 0 | 0 | 0 | 0
4 | 4 | 2020-07-01 | 2020-09-30 | 53961.68 | 863386.88 | 21287 | 926223 | 107.2779 | 205028.32 | 3280453.12 | 177878 | 3318593 | 101.1626 | 2400 | 38400 | 0 | 43425 | 113.0859 | 0 | 0 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 53961.68 | 917348.56 | 0 | 926223 | 100.9674 | 205028.32 | 3485481.44 | 1036579 | 4355172 | 124.9518 | 2400 | 40800 | 2500 | 45925 | 112.5613 | 0 | 0 | 0 | 0
5 | 2 | 2021-01-01 | 2021-03-31 | 53961.68 | 971310.24 | 0 | 926223 | 95.3581 | 205028.32 | 3690509.76 | 495911 | 4851083 | 131.4475 | 2400 | 43200 | 2500 | 48425 | 112.0949 | 0 | 0 | 0 | 0
5 | 3 | 2021-04-01 | 2021-06-30 | 53961.68 | 1025271.92 | 0 | 926223 | 90.3393 | 205028.32 | 3895538.08 | 126685 | 4977768 | 127.7813 | 2400 | 45600 | 0 | 48425 | 106.1952 | 0 | 0 | 0 | 0
5 | 4 | 2021-07-01 | 2021-09-30 | 53961.68 | 1079233.6 | 0 | 926223 | 85.8223 | 205028.32 | 4100566.4 | 755 | 4978523 | 121.4106 | 2400 | 48000 | 1000 | 49425 | 102.9688 | 0 | 0 | 0 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 53961.68 | 1133195.28 | 0 | 926223 | 81.7355 | 205028.32 | 4305594.72 | 0 | 4978523 | 115.6292 | 2400 | 50400 | 0 | 49425 | 98.0655 | 0 | 0 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 53961.68 | 1187156.96 | 0 | 926223 | 78.0203 | 205028.32 | 4510623.04 | 0 | 4978523 | 110.3733 | 2400 | 52800 | 0 | 49425 | 93.608 | 0 | 0 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 53961.68 | 1241118.64 | 0 | 926223 | 74.6281 | 205028.32 | 4715651.36 | 0 | 4978523 | 105.5745 | 2400 | 55200 | 0 | 49425 | 89.538 | 0 | 0 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 53961.68 | 1295080.32 | 0 | 926223 | 71.5186 | 205028.32 | 4920679.68 | 0 | 4978523 | 101.1755 | 2400 | 57600 | 0 | 49425 | 85.8073 | 0 | 0 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | 53961.68 | 1349042 |  | 926223 | 68.6578 | 205028.32 | 5125708 |  | 4978523 | 97.1285 | 2400 | 60000 |  | 49425 | 82.375 | 18200 |  | 6
7 | 2 | 2023-01-01 | 2023-03-31 |  | 1349042 | 422819 | 1349042 | 100 |  |  | 136758 | 5115281 |  |  | 60000 | 10575 | 60000 | 100
|  |  |  | 1349042 | TOTAL | 1349042 | BALANCE | 0 | 5115281 | TOTAL | 5115281 | BALANCE | 0 | 60000 | TOTAL | 60000 | BALANCE | 0 | 18200 | 0 | 6 | 0
|  | Closed | 2022-12-31
60 days expires March 2, 2023

## HSEMD
HSEMD CONTRACT SPENDING SUMMARY
Activity Center |  |  |  | Activity 172 Planning |  |  |  | Activity 181-01 Admin
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Spent | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Spent | Deliverables Projected | Deliverables Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 73094.08 | 73094.08 | 0 | 0 | 11896 | 11896 | 0 | 0 | 0 | 1
1 | 2 | 2017-01-01 | 2017-03-31 | 73094.08 | 146188.16 | 2227 | 2227 | 11896 | 23792 | 26351 | 26351 | 0 | 1
1 | 3 | 2017-04-01 | 2017-06-30 | 73094.08 | 219282.24 | 36610 | 38837 | 11896 | 35688 | 29183 | 55534 | 0 | 1
1 | 4 | 2017-07-01 | 2017-09-30 | 73094.08 | 292376.32 | 84505 | 123342 | 11896 | 47584 | 10717 | 66251 | 0 | 1
2 | 1 | 2017-10-01 | 2017-12-31 | 73094.08 | 365470.4 | 117076 | 240418 | 11896 | 59480 | 4407 | 70658 | 0 | 1
2 | 2 | 2018-01-01 | 2018-03-31 | 73094.08 | 438564.48 | 130184 | 370602 | 11896 | 71376 | 221 | 70879 | 0 | 1
2 | 3 | 2018-04-01 | 2018-06-30 | 73094.08 | 511658.56 | 141076 | 511678 | 11896 | 83272 | 1148 | 72027 | 0 | 1
2 | 4 | 2018-07-01 | 2018-09-30 | 73094.08 | 584752.64 | 138298 | 649976 | 11896 | 95168 | 986 | 73013 | 0 | 2
3 | 1 | 2018-10-01 | 2018-12-31 | 73094.08 | 657846.72 | 108200 | 758176 | 11896 | 107064 | 1177 | 74190 | 0 | 1
3 | 2 | 2019-01-01 | 2019-03-31 | 73094.08 | 730940.8 | 171689 | 929865 | 11896 | 118960 | 1304 | 75494 | 0 | 1
3 | 3 | 2019-04-01 | 2019-06-30 | 73094.08 | 804034.88 | 140715 | 1070580 | 11896 | 130856 | 920 | 76414 | 0 | 1
3 | 4 | 2019-07-01 | 2019-09-30 | 73094.08 | 877128.96 | 100595 | 1171175 | 11896 | 142752 | 1014 | 77428 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 73094.08 | 950223.04 | 158844 | 1330019 | 11896 | 154648 | 4103 | 81531 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 73094.08 | 1023317.12 | 90949 | 1420968 | 11896 | 166544 | 21355 | 102886 | 0 | 2
4 | 3 | 2020-04-01 | 2020-06-30 | 73094.08 | 1096411.2 | 96902 | 1517870 | 11896 | 178440 | 28698 | 131584 | 0 | 1
4 | 4 | 2020-07-01 | 2020-09-30 | 73094.08 | 1169505.28 | 27080 | 1544950 | 11896 | 190336 | 15693 | 147277 | 0 | 1
5 | 1 | 2020-10-01 | 2020-12-31 | 73094.08 | 1242599.36 | 30564 | 1575514 | 11896 | 202232 | 11089 | 158366 | 0 | 1
5 | 2 | 2021-01-01 | 2021-03-31 | 73094.08 | 1315693.44 | 68764 | 1644278 | 11896 | 214128 | 49926 | 208292 | 20 | 1
5 | 3 | 2021-04-01 | 2021-06-30 | 73094.08 | 1388787.52 | 62639 | 1706917 | 11896 | 226024 | 13222 | 221514 | 10 | 10
5 | 4 | 2021-07-01 | 2021-09-30 | 73094.08 | 1461881.6 | 44610 | 1751527 | 11896 | 237920 | 11913 | 233427 | 1 | 43
6 | 1 | 2021-10-01 | 2021-12-31 | 73094.08 | 1534975.68 | 9154 | 1760681 | 11896 | 249816 | 867 | 234294 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 73094.08 | 1608069.76 | 43652 | 1804333 | 11896 | 261712 | 8164 | 242458 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 73094.08 | 1681163.84 | 0 | 1804333 | 11896 | 273608 | 0 | 242458 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 73094.08 | 1754257.92 | 3594 | 1807927 | 11896 | 285504 | 3851 | 246309 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | 73094.08 | 1827352 | 888 | 1808815 | 11896 | 297400 | 1191 | 247500 | 44 | 2
7 | 2 | 2023-01-01 | 2023-03-31 |  |  | 4578 | 1813393 |  |  | 11748 | 259248 | 75 | 75
|  |  |  | 1813393 | TOTAL | BALANCE | 0 | 259248 | TOTAL | BALANCE | 0 | TOTAL | TOTAL

## Univ of Iowa
UNIVERSITY OF IOWA
Activity Center |  |  |  | Activity 172 Planning
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Spent | Deliverables Projected | Deliverables Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 258875.04 | 258875.04 | 0 | 0 | 0 | 1
1 | 2 | 2017-01-01 | 2017-03-31 | 258875.04 | 517750.08 | 0 | 0 | 0 | 1
1 | 3 | 2017-04-01 | 2017-06-30 | 258875.04 | 776625.12 | 901966 | 901966 | 0 | 2
1 | 4 | 2017-07-01 | 2017-09-30 | 258875.04 | 1035500.16 | 625534 | 1527500 | 0 | 1
2 | 1 | 2017-10-01 | 2017-12-31 | 258875.04 | 1294375.2 | 560963 | 2088463 | 0 | 1
2 | 2 | 2018-01-01 | 2018-03-31 | 258875.04 | 1553250.24 | 449738 | 2538201 | 0 | 0
2 | 3 | 2018-04-01 | 2018-06-30 | 258875.04 | 1812125.28 | 582730 | 3120931 | 0 | 0
2 | 4 | 2018-07-01 | 2018-09-30 | 258875.04 | 2071000.32 | 278917 | 3399848 | 0 | 0
3 | 1 | 2018-10-01 | 2018-12-31 | 258875.04 | 2329875.36 | 304662 | 3704510 | 0 | 35
3 | 2 | 2019-01-01 | 2019-03-31 | 258875.04 | 2588750.4 | 207668 | 3912178 | 0 | 1
3 | 3 | 2019-04-01 | 2019-06-30 | 258875.04 | 2847625.44 | 275180 | 4187358 | 0 | 9
3 | 4 | 2019-07-01 | 2019-09-30 | 258875.04 | 3106500.48 | 173033 | 4360391 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 258875.04 | 3365375.52 | 264771 | 4625162 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 258875.04 | 3624250.56 | 198275 | 4823437 | 0 | 1
4 | 3 | 2020-04-01 | 2020-06-30 | 258875.04 | 3883125.6 | 214144 | 5037581 | 0 | 1
4 | 4 | 2020-07-01 | 2020-09-30 | 258875.04 | 4142000.64 | 103813 | 5141394 | 0 | 0
5 | 1 | 2020-10-01 | 2020-12-31 | 258875.04 | 4400875.68 | 220264 | 5361658 | 0 | 1
5 | 2 | 2021-01-01 | 2021-03-31 | 258875.04 | 4659750.72 | 240614 | 5602272 | 57 | 1
5 | 3 | 2021-04-01 | 2021-06-30 | 258875.04 | 4918625.76 | 165351 | 5767623 | 1 | 1
5 | 4 | 2021-07-01 | 2021-09-30 | 258875.04 | 5177500.8 | 185372 | 5952995 | 1 | 3
6 | 1 | 2021-10-01 | 2021-12-31 | 258875.04 | 5436375.84 | 63707 | 6016702 | 0 | 1
6 | 2 | 2022-01-01 | 2022-03-31 | 258875.04 | 5695250.88 | 168693 | 6185395 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 258875.04 | 5954125.92 | 41440 | 6226835 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 258875.04 | 6213000.96 | 89118 | 6315953 | 0 | 19
7 | 1 | 2022-10-01 | 2022-12-31 | 258875.04 | 6471876 | 115522 | 6431475 | 27 | 5
7 | 2 | 2023-01-01 | 2023-03-31 |  |  | 40401 | 6471876 | 86 | 86
|  |  |  | 6471876 | TOTAL | BALANCE | 0 | TOTAL | TOTAL

## Iowa DNR
IOWA DNR
Activity Center |  |  |  | Activity 172 Planning
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Spent | Deliverables Projected | Deliverables Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 24693.88 | 24693.88 | 0 | 0 | 0 | 2
1 | 2 | 2017-01-01 | 2017-03-31 | 24693.88 | 49387.76 | 23014 | 23014 | 0 | 1
1 | 3 | 2017-04-01 | 2017-06-30 | 24693.88 | 74081.64 | 8297 | 31311 | 0 | 4
1 | 4 | 2017-07-01 | 2017-09-30 | 24693.88 | 98775.52 | 127471 | 158782 | 0 | 5
2 | 1 | 2017-10-01 | 2017-12-31 | 24693.88 | 123469.4 | 0 | 158782 | 0 | 1
2 | 2 | 2018-01-01 | 2018-03-31 | 24693.88 | 148163.28 | 81777 | 240559 | 0 | 1
2 | 3 | 2018-04-01 | 2018-06-30 | 24693.88 | 172857.16 | 39168 | 279727 | 0 | 1
2 | 4 | 2018-07-01 | 2018-09-30 | 24693.88 | 197551.04 | 45782 | 325509 | 0 | 1
3 | 1 | 2018-10-01 | 2018-12-31 | 24693.88 | 222244.92 | 0 | 325509 | 0 | 1
3 | 2 | 2019-01-01 | 2019-03-31 | 24693.88 | 246938.8 | 59237 | 384746 | 0 | 1
3 | 3 | 2019-04-01 | 2019-06-30 | 24693.88 | 271632.68 | 19288 | 404034 | 0 | 1
3 | 4 | 2019-07-01 | 2019-09-30 | 24693.88 | 296326.56 | 34428 | 438462 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 24693.88 | 321020.44 | 0 | 438462 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 24693.88 | 345714.32 | 48580 | 487042 | 0 | 1
4 | 3 | 2020-04-01 | 2020-06-30 | 24693.88 | 370408.2 | 11664 | 498706 | 0 | 9
4 | 4 | 2020-07-01 | 2020-09-30 | 24693.88 | 395102.08 | 13519 | 512225 | 0 | 1
5 | 1 | 2020-10-01 | 2020-12-31 | 24693.88 | 419795.96 | 0 | 512225 | 0 | 10
5 | 2 | 2021-01-01 | 2021-03-31 | 24693.88 | 444489.84 | 14671 | 526896 | 43 | 1
5 | 3 | 2021-04-01 | 2021-06-30 | 24693.88 | 469183.72 | 8846 | 535742 | 1 | 1
5 | 4 | 2021-07-01 | 2021-09-30 | 24693.88 | 493877.6 | 4246 | 539988 | 2 | 2
6 | 1 | 2021-10-01 | 2021-12-31 | 24693.88 | 518571.48 | 0 | 539988 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 24693.88 | 543265.36 | 4567 | 544555 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 24693.88 | 567959.24 | 0 | 544555 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 24693.88 | 592653.12 | 29932 | 574487 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | 24693.88 | 617347 | 20201 | 594688 | 2 | 2
7 | 2 | 2023-01-01 | 2023-03-31 |  |  | 21014 | 615702 | 48 | 48
|  |  |  | 615702 | TOTAL | BALANCE | 0 | TOTAL | TOTAL

## Univ of N Iowa
UNIVERSITY OF NORTHERN IOWA
Activity Center |  |  |  | Activity 172 Planning
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Spent | Deliverables Projected | Deliverables Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 17550 | 17550 | 0 | 0 | 0 | 1
1 | 2 | 2017-01-01 | 2017-03-31 | 17550 | 35100 | 20488 | 20488 | 0 | 1
1 | 3 | 2017-04-01 | 2017-06-30 | 17550 | 52650 | 8973 | 29461 | 0 | 1
1 | 4 | 2017-07-01 | 2017-09-30 | 17550 | 70200 | 0 | 29461 | 0 | 1
2 | 1 | 2017-10-01 | 2017-12-31 | 17550 | 87750 | 29806 | 59267 | 0 | 1
2 | 2 | 2018-01-01 | 2018-03-31 | 17550 | 105300 | 17671 | 76938 | 0 | 1
2 | 3 | 2018-04-01 | 2018-06-30 | 17550 | 122850 | 28060 | 104998 | 0 | 1
2 | 4 | 2018-07-01 | 2018-09-30 | 17550 | 140400 | 21451 | 126449 | 0 | 17
3 | 1 | 2018-10-01 | 2018-12-31 | 17550 | 157950 | 25689 | 152138 | 0 | 1
3 | 2 | 2019-01-01 | 2019-03-31 | 17550 | 175500 | 24790 | 176928 | 0 | 2
3 | 3 | 2019-04-01 | 2019-06-30 | 17550 | 193050 | 30201 | 207129 | 0 | 1
3 | 4 | 2019-07-01 | 2019-09-30 | 17550 | 210600 | 12915 | 220044 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 17550 | 228150 | 43059 | 263103 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 17550 | 245700 | 20389 | 283492 | 0 | 1
4 | 3 | 2020-04-01 | 2020-06-30 | 17550 | 263250 | 13598 | 297090 | 0 | 1
4 | 4 | 2020-07-01 | 2020-09-30 | 17550 | 280800 | 9899 | 306989 | 0 | 1
5 | 1 | 2020-10-01 | 2020-12-31 | 17550 | 298350 | 24756 | 331745 | 0 | 1
5 | 2 | 2021-01-01 | 2021-03-31 | 17550 | 315900 | 36844 | 368589 | 34 | 1
5 | 3 | 2021-04-01 | 2021-06-30 | 17550 | 333450 | 12575 | 381164 | 1 | 1
5 | 4 | 2021-07-01 | 2021-09-30 | 17550 | 351000 | 1667 | 382831 | 1 | 0
6 | 1 | 2021-10-01 | 2021-12-31 | 17550 | 368550 | 6240 | 389071 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 17550 | 386100 | 9643 | 398714 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 17550 | 403650 | 7537 | 406251 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 17550 | 421200 | 7791 | 414042 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | 17550 | 438750 | 18945 | 432987 | 1 | 1
7 | 2 | 2023-01-01 | 2023-03-31 |  |  | 5694.14 | 438681.14 | 37 | 37
|  |  |  | 438681.14 | TOTAL | BALANCE | 0 | TOTAL | TOTAL

## Iowa State Univ
IOWA STATE UNIVERSITY
Activity Center |  |  |  | Activity 172 Planning
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Spent | Deliverables Projected | Deliverables Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 84500 | 84500 | 0 | 0 | 0 | 1
1 | 2 | 2017-01-01 | 2017-03-31 | 84500 | 169000 | 69819 | 69819 | 0 | 1
1 | 3 | 2017-04-01 | 2017-06-30 | 84500 | 253500 | 0 | 69819 | 0 | 1
1 | 4 | 2017-07-01 | 2017-09-30 | 84500 | 338000 | 113478 | 183297 | 0 | 1
2 | 1 | 2017-10-01 | 2017-12-31 | 84500 | 422500 | 78332 | 261629 | 0 | 1
2 | 2 | 2018-01-01 | 2018-03-31 | 84500 | 507000 | 70377 | 332006 | 0 | 1
2 | 3 | 2018-04-01 | 2018-06-30 | 84500 | 591500 | 122199 | 454205 | 0 | 1
2 | 4 | 2018-07-01 | 2018-09-30 | 84500 | 676000 | 188640 | 642845 | 0 | 1
3 | 1 | 2018-10-01 | 2018-12-31 | 84500 | 760500 | 121585 | 764430 | 0 | 2
3 | 2 | 2019-01-01 | 2019-03-31 | 84500 | 845000 | 77029 | 841459 | 0 | 1
3 | 3 | 2019-04-01 | 2019-06-30 | 84500 | 929500 | 100290 | 941749 | 0 | 1
3 | 4 | 2019-07-01 | 2019-09-30 | 84500 | 1014000 | 29569 | 971318 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 84500 | 1098500 | 148882 | 1120200 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 84500 | 1183000 | 51743 | 1171943 | 0 | 1
4 | 3 | 2020-04-01 | 2020-06-30 | 84500 | 1267500 | 154258 | 1326201 | 0 | 1
4 | 4 | 2020-07-01 | 2020-09-30 | 84500 | 1352000 | 0 | 1326201 | 0 | 1
5 | 1 | 2020-10-01 | 2020-12-31 | 84500 | 1436500 | 0 | 1326201 | 0 | 1
5 | 2 | 2021-01-01 | 2021-03-31 | 84500 | 1521000 | 217431 | 1543632 | 18 | 1
5 | 3 | 2021-04-01 | 2021-06-30 | 84500 | 1605500 | 31393 | 1575025 | 1 | 1
5 | 4 | 2021-07-01 | 2021-09-30 | 84500 | 1690000 | 136628 | 1711653 | 1 | 5
6 | 1 | 2021-10-01 | 2021-12-31 | 84500 | 1774500 | 56339 | 1767992 | 0 | 0
6 | 2 | 2022-01-01 | 2022-03-31 | 84500 | 1859000 | 57198 | 1825190 | 0 | 0
6 | 3 | 2022-04-01 | 2022-06-30 | 84500 | 1943500 | 38118 | 1863308 | 0 | 0
6 | 4 | 2022-07-01 | 2022-09-30 | 84500 | 2028000 | 76602 | 1939910 | 0 | 0
7 | 1 | 2022-10-01 | 2022-12-31 | 84500 | 2112500 | 59774.46 | 1999684.46 | 14 | 9
7 | 2 | 2023-01-01 | 2023-03-31 |  |  | 60696.99 | 2060381.45 | 34 | 34
|  |  |  | 2060381.45 | TOTAL | BALANCE | 0 | TOTAL | TOTAL

## IDALS
IDALS
Activity Center |  |  |  | Activity 172 Planning
Year | Quarter | Start Date | End Date | Quarter $ Projection | Cumulative $ Spent Projection | Actual Quarter $ Spent | Actual Spent | Deliverables Projected | Deliverables Completed
1 | 1 | 2016-10-01 | 2016-12-31 | 10714.2857 | 10714.2857 | 0 | 0 | 0 | 1
1 | 2 | 2017-01-01 | 2017-03-31 | 10714.2857 | 21428.5714 | 4515 | 4515 | 0 | 4
1 | 3 | 2017-04-01 | 2017-06-30 | 10714.2857 | 32142.8571 | 7866 | 12381 | 0 | 1
1 | 4 | 2017-07-01 | 2017-09-30 | 10714.2857 | 42857.1429 | 14569 | 26950 | 0 | 1
2 | 1 | 2017-10-01 | 2017-12-31 | 10714.2857 | 53571.4286 | 10524 | 37474 | 0 | 1
2 | 2 | 2018-01-01 | 2018-03-31 | 10714.2857 | 64285.7143 | 12412 | 49886 | 0 | 8
2 | 3 | 2018-04-01 | 2018-06-30 | 10714.2857 | 75000 | 10028 | 59914 | 0 | 1
2 | 4 | 2018-07-01 | 2018-09-30 | 10714.2857 | 85714.2857 | 16314 | 76228 | 0 | 1
3 | 1 | 2018-10-01 | 2018-12-31 | 10714.2857 | 96428.5714 | 2023 | 78251 | 0 | 1
3 | 2 | 2019-01-01 | 2019-03-31 | 10714.2857 | 107142.8571 | 15692 | 93943 | 0 | 1
3 | 3 | 2019-04-01 | 2019-06-30 | 10714.2857 | 117857.1429 | 9433 | 103376 | 0 | 1
3 | 4 | 2019-07-01 | 2019-09-30 | 10714.2857 | 128571.4286 | 13354 | 116730 | 0 | 1
4 | 1 | 2019-10-01 | 2019-12-31 | 10714.2857 | 139285.7143 | 10547 | 127277 | 0 | 1
4 | 2 | 2020-01-01 | 2020-03-31 | 10714.2857 | 150000 | 14254 | 141531 | 0 | 1
4 | 3 | 2020-04-01 | 2020-06-30 | 10714.2857 | 160714.2857 | 10331 | 151862 | 0 | 1
4 | 4 | 2020-07-01 | 2020-09-30 | 10714.2857 | 171428.5714 | 16483 | 168345 | 0 | 1
5 | 1 | 2020-10-01 | 2020-12-31 | 10714.2857 | 182142.8571 | 0 | 168345 | 0 | 1
5 | 2 | 2021-01-01 | 2021-03-31 | 10714.2857 | 192857.1429 | 25462 | 193807 | 28 | 1
5 | 3 | 2021-04-01 | 2021-06-30 | 10714.2857 | 203571.4286 | 12690 | 206497 | 1 | 1
5 | 4 | 2021-07-01 | 2021-09-30 | 10714.2857 | 214285.7143 | 12254 | 218751 | 1 | 1
6 | 1 | 2021-10-01 | 2021-12-31 | 10714.2857 | 225000 | 6249 | 225000 | 8 | 8
5 | 3 | 2021-04-01 | 2021-06-30
5 | 4 | 2021-07-01 | 2021-09-30
6 | 1 | 2021-10-01 | 2021-12-31
6 | 2 | 2022-01-01 | 2022-03-31
6 | 3 | 2022-04-01 | 2022-06-30
6 | 4 | 2022-07-01 | 2022-09-30
7 | 1 | 2022-10-01 | 2022-12-31
7 | 2 | 2023-01-01 | 2023-03-31 |  |  |  |  | 38 | 32
|  |  |  | 225000 | TOTAL | BALANCE | 0 | TOTAL | TOTAL